## Dashboard
NCC Audit Reform and LGR Obligations Tracker
Live status snapshot · Refreshed 11 July 2026
19 |  | 1 |  |  | 4 |  | 1
OBLIGATIONS |  | OVERDUE |  |  | DUE IN 30 DAYS |  | COMPLETE
OBLIGATIONS OVERVIEW
Obligations by Status |  | Obligations by Risk |  |  | Obligations by Theme
Status | Count | Risk Rating | Count |  | Theme | Count
Not started | 1 | High | 15 |  | Governance and Transparency | 7
In progress | 9 | Medium | 4 |  | LGR Transition | 6
Complete | 1 | Low | 0 |  | Financial Reporting | 3
Blocked | 0 |  |  |  | Audit Procurement | 2
Ongoing | 8 |  |  |  | Internal Controls | 1
ACTIONS & INTELLIGENCE FEED
Action Summary | Count | Intelligence Feed | Count
Total actions | 9 | Items captured | 68
In progress | 1 | Flagged material | 30
Complete | 1 | Material (last 30 days) | 0
Overdue | 2 | Awaiting review | 68
Avg. progress | 17%
Evidence coverage | 100%
ATTENTION NEEDED
ID | Obligation | Owner | Target | Status
OB-A2 | NCC must prepare and agree the Continuous Service Improvement Plan (CSIP) with t | Sajeeda Rose (Chief Executive) | 24 Jun 2026 | Overdue
OB-A7 | NCC must respond to each recommendation in the external auditor's Annual Report | Gareth Robinson (Director of Finance) | 31 Jul 2026 | Due soon
OB-A9 | NCC must produce and publish an Annual Governance Statement reflecting the counc | Beth Brown (Strategic Director of Legal and Governance) | 31 Jul 2026 | Due soon
OB-A11 | NCC must progress the open items on the Audit Committee Recommendation Tracker t | Kate Morris (Scrutiny and Audit Support Officer) | 31 Jul 2026 | Due soon
OB-L5 | NCC must review its governance, audit committee arrangements, and successor body | Beth Brown (Strategic Director of Legal and Governance) | 31 Jul 2026 | Due soon

## Intelligence
Date Found | Title | Source | Category | Published | Material | Matched | Theme | URL | Reviewed | Notes | Hash
2026-06-08 | Local Audit Office Chair: the government’s preferred candidate | GOV.UK | Correspondence | 2026-05-26 | Yes | Audit; Manually elevated - material legislative/appointment development (Audit) | Audit Procurement | https://www.gov.uk/government/publications/local-audit-office-chair-the-governments-preferred-candidate |  |  | 29225ec1a415a81cf231e2c32c5a19de
2026-06-08 | Local government reorganisation: implementation guidance | GOV.UK | Guidance | 2026-05-21 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-implementation-guidance |  |  | 774a562d1fcbe994282fb838ddc67712
2026-06-08 | Local government reorganisation: Policy and programme updates | GOV.UK | Collection | 2026-03-12 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/collections/local-government-reorganisation-policy-and-programme-updates |  |  | 4d80bb6766cc36845f3aaa63ed38032e
2026-06-08 | Nottinghamshire and Nottingham: Local government reorganisation | GOV.UK | Guidance | 2026-02-05 | Yes | Local, Transition | LGR Transition | https://www.gov.uk/government/collections/nottinghamshire-and-nottingham-local-government-reorganisation |  |  | 438de41b33123f97381da2a9ae88434e
2026-06-08 | Local government reorganisation: summary of feedback on interim plans | GOV.UK | Guidance | 2025-06-03 | Yes | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-summary-of-feedback-on-interim-plans |  |  | f9370765871b9fce3681e7465d2c31d4
2026-06-08 | ​​English Devolution White Paper​: Power and partnership: Foundations for growth | GOV.UK | Guidance | 2024-12-16 | Yes | Transition; Manually elevated - material legislative/appointment development (LGR Transition / Audit) | LGR Transition | https://www.gov.uk/government/publications/english-devolution-white-paper-power-and-partnership-foundations-for-growth |  |  | 95a642b258a7dc8e0061bfa8718344dc
2026-06-08 | Local government reorganisation: update on Secretary of State's decision regarding local elections of May 2026 | GOV.UK | Guidance | 2026-02-16 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-update-on-secretary-of-states-decision-regarding-local-elections-of-may-2026 |  |  | 8ef81633f5a750cb4c1ac14f8479b5df
2026-06-08 | Local government reorganisation: further letters to councils on local elections in May 2026 | GOV.UK | Guidance | 2026-01-29 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-further-letters-to-councils-on-local-elections-in-may-2026 |  |  | f0ca28d88494d6a9496f00f5172c71a1
2026-06-08 | ​​​Local government reorganisation: further letter to council leaders with elections in May 2026 | GOV.UK | Guidance | 2026-01-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-further-letter-to-council-leaders-with-elections-in-may-2026 |  |  | ebf079237d298efbcef8d2e05ff2e464
2026-06-08 | ​​​Local government reorganisation: letter to council leaders with elections in May 2026 | GOV.UK | Guidance | 2025-12-18 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-council-leaders-with-elections-in-may-2026 |  |  | c7adda5c60a04c17e302af0273366e2d
2026-06-08 | Local government reorganisation: letter to leaders on publicity code | GOV.UK | Guidance | 2025-11-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-leaders-on-publicity-code |  |  | 4fc0d66b0cbc7e1557ee2aa32833ef79
2026-06-08 | Local government reorganisation: letter to areas invited to submit final proposals | GOV.UK | Guidance | 2025-07-24 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals |  |  | 22d3f1b0d8f5579612f7cafd74384940
2026-06-08 | Local government reorganisation: letter to two-tier areas | GOV.UK | Guidance | 2025-01-15 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-two-tier-areas |  |  | 7dc6f9cdf34308af597518ba42239ab4
2026-06-08 | Local Government Reorganisation Advisory Group | GOV.UK | Guidance | 2026-05-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/groups/local-government-reorganisation-advisory-group |  |  | deb9b24ab99e8ba843c7fbc64c5e2ebb
2026-06-08 | Local government reorganisation in Nottinghamshire and Nottingham | GOV.UK | Guidance | 2026-02-05 | Yes | Local, Transition | LGR Transition | https://www.gov.uk/government/consultations/local-government-reorganisation-in-nottinghamshire-and-nottingham |  |  | 205848d9300953ace55c2f3f63b58552
2026-06-08 | Local government reorganisation: letter to council leaders | GOV.UK | Guidance | 2026-02-05 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-council-leaders |  |  | b4fe184485e89661bc66c4738064cf08
2026-06-08 | Local audit reform | GOV.UK | Collection | 2025-12-02 | Unclear | Audit | Other | https://www.gov.uk/government/publications/local-audit-reform |  |  | 45fb6decc9967abb65dbfdbd6215b69b
2026-06-08 | Statutory intervention: Nottingham City Council | GOV.UK | Collection | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/collections/statutory-intervention-nottingham-city-council-minded-to-decision |  |  | c2dc55e3a57ff4e8f558291afcc1fc0b
2026-06-08 | Nottingham City Council: Letter to Chief Executive (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-chief-executive-24-march-2026 |  |  | 2898065a8f868eaa7fd43bbd82585e3c
2026-06-08 | Nottingham City Council: Ministerial Envoy appointment letter | GOV.UK | Guidance | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-envoy-appointment-letter |  |  | 2dbede6274db13509cc24e5283575c92
2026-06-08 | Nottingham City Council: Letter to former Commissioners (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-former-commissioners-24-march-2026 |  |  | 9fda66e1dc31a97df966b7bfb61d2152
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-24-march-2026 |  |  | 8035e4e92865a4e08aa53357659b4d9c
2026-06-08 | Nottingham City Council: Explanatory Memorandum (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-24-march-2026 |  |  | d3c467457b540a3f0bf614309aca9c19
2026-06-08 | Nottingham City Council: Representation (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation-24-march-2026 |  |  | 26fc51c10335d44f7a857673c0b0187d
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (4 February 2026) | GOV.UK | Guidance | 2026-02-04 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-4-february-2026 |  |  | 560ce0c0352c0e6f61e7726b7b64345b
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ fourth report | GOV.UK | Guidance | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-fourth-report |  |  | 600b6f4d89eb5413e08733526ceca1ed
2026-06-08 | Nottingham City Council: Commissioners’ fourth report | GOV.UK | Guidance | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-fourth-report |  |  | 99a0b5064ee8727c2347c9b72571b15b
2026-06-08 | Nottingham City Council: Explanatory Memorandum (updated 21 November 2025) | GOV.UK | Guidance | 2025-11-21 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-updated-21-november-2025 |  |  | 801a9c9285e4a5e78e6fc55a1359a162
2026-06-08 | Nottingham City Council: Commissioner appointment letters (updated 21 November 2025) | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioner-appointment-letters-updated-21-november-2025 |  |  | 6251f19915a405867e8db673d2d1d536
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ third report | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-third-report |  |  | 057d2e3166a08ecb5b94d555e58217d4
2026-06-08 | Nottingham City Council: Commissioners’ third report | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-third-report |  |  | 8c8111a055eaa3d14e02d4500ccb6cb3
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ second report | GOV.UK | Guidance | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-second-report |  |  | cd73ff777fc694dab66f6b876a1c1c28
2026-06-08 | Nottingham City Council: Commissioners’ second report | GOV.UK | Guidance | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-second-report |  |  | d0c04d111712ea0ef8f01685db7108d2
2026-06-08 | Nottingham City Council: Exceptional Financial Support request 2025-26 | GOV.UK | Guidance | 2025-03-13 | Yes | Local, Intervention | Other | https://www.gov.uk/government/publications/nottingham-city-council-exceptional-financial-support-request-2025-26 |  |  | 5c4c10fa46b25394fc2cd21fe1c1d75f
2026-06-08 | Nottingham City Council: Ministerial response to Commissioners’ first report | GOV.UK | Guidance | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-commissioners-first-report |  |  | 71f2e56afb6d6753e35b172cc516b431
2026-06-08 | Nottingham City Council: Commissioners' first report | GOV.UK | Guidance | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-first-report |  |  | d98ca8e7ad028a097ebc6dda8f8e5aa3
2026-06-08 | Nottingham City Council Improvement and Assurance Board: final report | GOV.UK | Guidance | 2024-05-16 | Yes | Local | Internal Controls | https://www.gov.uk/government/publications/nottingham-city-council-improvement-and-assurance-board-final-report |  |  | b2a8fea237a904bd7678992fd8043a00
2026-06-08 | ​​Nottingham City Council: Explanatory Memorandum (updated 11 April 2024)​ | GOV.UK | Guidance | 2024-04-11 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-updated-11-april-2024 |  |  | b8cca80ece289181cd7b9f904d30f831
2026-06-08 | Nottingham City Council: Commissioner appointment letters | GOV.UK | Guidance | 2024-04-11 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioner-appointment-letters-22-february-2024 |  |  | 3ca747b43d32cba56433c1fb3e64607a
2026-06-08 | Nottingham City Council: Exceptional Financial Support request 2024-25 | GOV.UK | Guidance | 2024-02-29 | Yes | Local, Intervention | Other | https://www.gov.uk/government/publications/nottingham-city-council-exceptional-financial-support-request-2024-25 |  |  | 0bb0ae6e9ccc3f81265482eab2db78a8
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-22-february-2024 |  |  | 17eeadd0b9d2a6883638b93980e8ae9f
2026-06-08 | Nottingham City Council: Ministerial letter to Sir Tony Redmond (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-letter-to-sir-tony-redmond-22-february-2024 |  |  | 2a180fc130afb8024014f66b839cde05
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-22-february-2024 |  |  | 145bba91104e4dbf70569b89dee1810a
2026-06-08 | Nottingham City Council: Explanatory Memorandum (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-22-february-2024 |  |  | 10fde9f6a7ebdf4a7a5e61c0cda234b2
2026-06-08 | Nottingham City Council: Representation (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation-22-february-2024 |  |  | 05f81d6e412bec89bd864b13642d9780
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond (18 May 2023) | GOV.UK | Guidance | 2023-05-18 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond-18-may-2023 |  |  | 3024293ec6dec3a33dac3ca850b5b94e
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond (2 February 2023) | GOV.UK | Guidance | 2023-02-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond-2-february-2023 |  |  | af06ed33550e77fcda0f12683c985793
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (2 September 2022) | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-2-september-2022 |  |  | 2a1175d02720975b8afb24a6fb1fb0da
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond |  |  | 33eef31789f3513e07cd9482e927715e
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (2 September 2022) | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-2-september-2022 |  |  | 3033603f989ae2332994a65f3ce3df47
2026-06-08 | Nottingham City Council: Explanatory Memorandum | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum |  |  | a1b9b1e7a30adb3476c5cb6cbf61526c
2026-06-08 | Nottingham City Council: Representation | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation |  |  | 7774e32cabdf3f56996920439013a737
2026-06-08 | Nottingham City Council: Letter to the Chief Executive | GOV.UK | Guidance | 2022-06-23 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive |  |  | d14b1f80d72f9a080f4127e336d3d554
2026-06-08 | Non-statutory review of Nottingham City Council | GOV.UK | Guidance | 2022-06-23 | Unclear | Local | Other | https://www.gov.uk/government/collections/non-statutory-review-of-nottingham-city-council |  |  | e512c646b828c631fbf72ad76fc7953a
2026-06-08 | English Devolution and Community Empowerment Act 2026 | Parliament | Bill |  | Yes | Transition; Manually elevated - material legislative/appointment development (LGR Transition / Audit) | LGR Transition | https://bills.parliament.uk/bills/4002 |  |  | 2cc0140e559129309466a2e5502e619e
2026-06-08 | Bill Butler named as preferred candidate for Local Audit Office Chair | PSAA | PSAA Update | 2026-06-08 | Yes | Audit; Manually elevated - material legislative/appointment development (Audit) | Audit Procurement | https://www.psaa.co.uk/2026/05/bill-butler-named-as-preferred-candidate-for-local-audit-office-chair/ |  |  | 217e8a844dbce9fac4bf4e2ffffd9c99
2026-06-08 | PSAA appoints Adrian Lythgo as new Board member | PSAA | PSAA Update | 2026-06-08 | Unclear | Audit | Audit Procurement | https://www.psaa.co.uk/2026/05/psaa-appoints-adrian-lythgo-as-new-board-member/ |  |  | 295e7fbfbe3919f6276fafbd7723ca11
2026-06-08 | English Devolution Bill receives Royal Assent | PSAA | PSAA Update | 2026-06-08 | Unclear | Transition | LGR Transition | https://www.psaa.co.uk/2026/04/english-devolution-bill-receives-royal-assent/ |  |  | ba312fc132d7eae858e78fe08546b660
2026-06-08 | Mayor joins partners as Nottingham launches bold City Vision | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/nottingham-city-vision/ |  |  | c02a3a1f32c99cbf8f89477289e4e686
2026-06-08 | Mayor welcomes Right to Request as 'devolution revolution' delivers for communities | EMCCA | Guidance |  | Unclear | Transition | LGR Transition | https://www.eastmidlands-cca.gov.uk/news/right-to-request/ |  |  | 55ae3f628fe09b311cad2563bb1a6772
2026-06-08 | Delight as Mayor helps open Nottingham's first major bridge over the Trent in almost 70 years | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/waterside-bridge-opens/ |  |  | c11a40c30dc7447bb458c4b1c001e5a7
2026-06-08 | Audit Committee — meeting 31 Jul 2026 9.30 am | NCC Committee | Committee Paper | 2026-07-31 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11775&Ver=4 |  |  | 9c81b083217b7e8f15e20e6550dcf8f7
2026-06-08 | Audit Committee — meeting 26 Jun 2026 9.30 am | NCC Committee | Committee Paper | 2026-06-26 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11601&Ver=4 |  |  | 988f05cdc883ae581691fd9dd43bc082
2026-06-08 | Audit Committee — meeting 27 Mar 2026 9.30 am | NCC Committee | Committee Paper | 2026-03-27 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11256&Ver=4 |  |  | 081e65a88e83aa5ca3c9e0aed7a2d2c3
2026-06-08 | Audit Committee — meeting 20 Feb 2026 9.30 am | NCC Committee | Committee Paper | 2026-02-20 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11255&Ver=4 |  |  | 7947dfbc1ac36c11ac3f5582a88d7f1a
2026-06-08 | Audit Committee — meeting 30 Jan 2026 9.30 am | NCC Committee | Committee Paper | 2026-01-30 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11477&Ver=4 |  |  | 8cbe63a69792be703749278df181fc09
2026-06-08 | Improvement Committee — meeting 26 Nov 2026 2.00 pm | NCC Committee | Committee Paper | 2026-11-26 | Yes | Local, Intervention | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=1175&MId=11731&Ver=4 |  |  | 1794f0fdfeb98b95d8b35be8cb10d0c4
2026-06-08 | Improvement Committee — meeting 4 Jun 2026 2.00 pm | NCC Committee | Committee Paper | 2026-06-04 | Yes | Local, Intervention | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=1175&MId=11730&Ver=4 |  |  | 996fb9ef9e75bca4bdbe62e7bfa5d568

## Obligations
Obligation ID | Obligation | Source / Trigger | Theme | Owner | Risk Rating | Target Date | Status | Evidence Required | Evidence Location | Sign Off By | Last Updated | Notes | Obligation Level
OB-A1 | NCC must establish the Continuous Improvement Committee with the required membership including Opposition Leaders, independent external leads for Adults and Children, and Ministerial Envoys. | Nottingham City Council: Directions made under the Local Government Act 1999 (24 March 2026) | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | High | 2026-06-04 | Complete | Committee Terms of Reference published; first meeting held with correct membership. | https://committee.nottinghamcity.gov.uk/documents/g11742/Public%20reports%20pack%2004th-Jun-2026%2014.00%20Improvement%20Committee.pdf | Improvement Committee / John | 2026-06-09 | Completed at the 4 June 2026 Improvement Committee meeting. Was part of the old OB-005 commissioner row. | Periodic
OB-A2 | NCC must prepare and agree the Continuous Service Improvement Plan (CSIP) with the Ministerial Envoys within three months of the 24 March 2026 directions. | 24 March 2026 Directions; Improvement Committee report 4 June 2026 | Governance and Transparency | Sajeeda Rose (Chief Executive) | High | 2026-06-24 | In progress | Improvement Committee endorsement minute; published CSIP document. |  | Improvement Committee / Ministerial Envoys | 2026-06-09 | MOST TIME-CRITICAL obligation. Deadline 24 June 2026 = three months from the 24 March 2026 directions. | Statutory
OB-A3 | NCC must embed improvements in financial management, savings delivery, accounts production, and capital programme governance. | 24 March 2026 Directions; CSIP Financial Sustainability and Management programme | Financial Reporting | Stuart Fair (Corporate Director for Finance and Resources, S151) | High |  | Ongoing | Audit Committee treasury and accounts papers; CSIP performance reporting; six-monthly Improvement Committee reports. |  | Improvement Committee | 2026-06-09 | SAO Finance: S Fair. Monitored six-monthly via the Improvement Committee. | Monitoring
OB-A4 | NCC must embed improvements in scrutiny and decision making across the council's governance arrangements. | 24 March 2026 Directions; CSIP Governance, Scrutiny and Decision Making programme | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | Medium |  | Ongoing | Improvement Committee reports; Corporate Scrutiny Committee papers; updated Scheme of Delegation. |  | Improvement Committee | 2026-06-09 | Ongoing CSIP programme. | Monitoring
OB-A5 | NCC must embed improvements in risk management and internal audit, including aligning the internal audit function with Local Audit Office standards and guidance and ensuring synergy with external assurance. | 24 March 2026 Directions; CSIP Risk Management and Internal Audit programme | Internal Controls | Lynne Dowdican (Head of Internal Audit) | High |  | Ongoing | Internal Audit Annual Plan and progress reports to Audit Committee; Head of Internal Audit opinion; alignment note against LAO standards. |  | Audit Committee | 2026-06-09 | Direct CSIP obligation: internal audit must align with LAO standards. Supported by D Bowring (Risk). | Monitoring
OB-A6 | NCC must cooperate with the Ministerial Envoys, provide access, and respond to their recommendations. | 24 March 2026 Directions | Governance and Transparency | Sajeeda Rose (Chief Executive) | High |  | Ongoing | Improvement Committee meeting records showing Envoy attendance; responses to Envoy recommendations. |  | Chief Executive / Improvement Committee | 2026-06-09 | Since 24 March 2026 the oversight structure uses Ministerial Envoys, not Commissioners. | Monitoring
OB-A7 | NCC must respond to each recommendation in the external auditor's Annual Report and Audit Findings (ISA 260). | Audit Committee 27 March 2026; External Audit Findings 2024/25 | Financial Reporting | Gareth Robinson (Director of Finance) | High | 2026-07-31 | In progress | Management response document; Audit Committee minute noting acceptance; completed action evidence for each recommendation. |  | Audit Committee | 2026-06-09 | Tie target to the next Audit Committee cycle. | Periodic
OB-A8 | NCC must produce and publish audited accounts with a signed audit opinion. | Accounts and Audit Regulations 2015; Audit Committee work programme | Financial Reporting | Stuart Fair (Corporate Director for Finance and Resources, S151) | High | 2026-09-30 | In progress | Published Statement of Accounts; auditor's opinion; note on any disclaimer. |  | Audit Committee | 2026-06-09 | Evidence Location must link to the SPECIFIC year's document on the Statement of Accounts page, not the homepage: https://www.nottinghamcity.gov.uk/your-council/about-the-council/statement-of-accounts-and-reports/ | Enduring
OB-A9 | NCC must produce and publish an Annual Governance Statement reflecting the council's current governance position and any significant weaknesses. | Accounts and Audit Regulations 2015; Audit Committee work programme July 2026 | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | High | 2026-07-31 | In progress | Published AGS; Audit Committee approval minute. | https://nottinghamcity.gov.uk | Audit Committee | 2026-06-09 | Target: July 2026 committee cycle. Draft AGS 2024/25 confirmed published online; awaiting Audit Committee approval minute. | Enduring
OB-A10 | NCC must understand and plan for how the Local Audit Office (LAO) transition affects its audit arrangements, and brief the Audit Committee. | PSAA abolition and Local Audit Office transition | Audit Procurement | Gareth Robinson (Director of Finance) | High | 2026-09-30 | In progress | Audit Committee briefing note on LAO implications; updated audit plan if needed. |  | Audit Committee | 2026-06-09 | PSAA-procured contract runs to 2027/28. Bill Butler named preferred LAO Chair candidate May 2026. Was the old OB-002. | Monitoring
OB-A11 | NCC must progress the open items on the Audit Committee Recommendation Tracker through to completion (see linked actions OB-A11.1, .2, .3). | Audit Committee minutes 20 February 2026; Recommendation Tracker | Governance and Transparency | Kate Morris (Scrutiny and Audit Support Officer) | Medium | 2026-07-31 | In progress | Recommendation Tracker rows moved from Pending to Responded; completion evidence for each sub-action. |  | Audit Committee | 2026-06-09 | Parent obligation. Three sub-actions live in the Actions tab: A11.1 (exemption benchmarking), A11.2 (Table 5 clarification), A11.3 (UN PRI/UNGP legal briefing). | Periodic
OB-A12 | NCC must integrate transitional accounting baselines derived from new oversight standards into local audit workflows. | Bill Butler named as preferred candidate for Local Audit Office Chair PSAA (8 June 2026) | Audit Procurement | Gareth Robinson (Director of Finance) | High | 2026-09-30 | In progress | Alignment strategy document approved by Audit Committee referencing new LAO framework parameters. | psaa.co.uk | Audit Committee | 2026-06-09 | NEW IMMINENT REQUIREMENT tracking transition handovers before ultimate PSAA abolition. | Periodic
OB-L1 | NCC must continue to work with other Nottinghamshire councils to define, coordinate, and implement safe day-one establishment of a new unitary authority. | 24 March 2026 Directions; CSIP LGR priority service improvement area | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High |  | Ongoing | Joint LGR committee papers; transition programme updates to Improvement Committee; cooperation records with other councils. |  | Chief Executive / Improvement Committee | 2026-06-09 | LGR sits under the Chief Executive and the Director of Policy. | Monitoring
OB-L2 | NCC must track the MHCLG consultation decision and respond to the statutory order implications for Nottinghamshire and Nottingham. | MHCLG consultation for Nottinghamshire and Nottingham (from 25 March 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High |  | Ongoing | Council response to consultation; record of statutory order decision; legal advice on transition implications. |  | Chief Executive | 2026-06-09 | CRITICAL MILESTONE: when the Secretary of State issues the final Statutory Boundary Order, OB-L6 becomes live (S151 asset/liability review). | Monitoring
OB-L3 | NCC must work toward safe and legal day-one establishment of the new unitary authority, including governance, service continuity, and asset and liability planning. | CSIP LGR priority area; MHCLG LGR implementation guidance (May 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High | 2027-05-01 | Ongoing | Transition programme plan; governance framework for shadow authority; service continuity planning documents. |  | Chief Executive / Improvement Committee | 2026-06-09 | Planning horizon: shadow authority elections approximately May 2027; Vesting Day approximately 1 April 2028. | Monitoring
OB-L4 | The internal audit plan must cover LGR transition risks including service demerger, asset and liability transfer, and governance during the shadow authority phase. | CSIP Risk Management and Internal Audit programme; seeded OB-004 | LGR Transition | Lynne Dowdican (Head of Internal Audit) | High | 2026-10-31 | In progress | Updated Internal Audit Annual Plan with an LGR transition section; Audit Committee approval. |  | Audit Committee | 2026-06-09 | Cross-track: also an Internal Controls obligation. Was the old OB-004. | Periodic
OB-L5 | NCC must review its governance, audit committee arrangements, and successor body governance in light of the English Devolution and Community Empowerment Act 2026 transparency and accountability codes. | English Devolution and Community Empowerment Act 2026 (Royal Assent confirmed) | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | Medium | 2026-07-31 | In progress | Formal gap analysis report to the July 2026 Audit Committee verifying the successor-body governance framework matches the 2026 Act, referencing the relevant Act sections against the current Audit Committee Terms of Reference and the proposed successor body governance model. |  | Audit Committee | 2026-06-09 | LGR legislative track. Detailed implementation timeline firms up as statutory guidance is issued. Was the old OB-001. | Periodic
OB-L6 | On issue of the final Statutory Boundary Order, the Section 151 Officer must review asset and liability arrangements for any items planned for transfer to the new unitary authority. | Statutory Boundary Order for the Nottingham/Nottinghamshire unitary structure (pending) | LGR Transition | Stuart Fair (Corporate Director for Finance and Resources, S151) | High |  | Not started | S151 finance review of asset and liability transfer arrangements; report to Audit / Improvement Committee. |  | Section 151 Officer / Audit Committee | 2026-06-09 | TRIGGER PENDING: this obligation only becomes live when the final Statutory Boundary Order is published (Guide Part 6). It is a formal finance review obligation, not a freeze of the asset registry — that remains the S151 Officer's decision. Set the Target Date when the order lands. | Periodic
OB-L7 | NCC must optimize regional demerger models to comply with newly issued national administrative transformation frameworks. | Local government reorganisation: implementation guidance GOV.UK (8 June 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | Medium |  | Ongoing | LGR working team minutes detailing structural compliance parameters mapped against the June 2026 layout guides. | www.gov.uk | Chief Executive / Improvement Committee | 2026-06-09 | NEW GUIDANCE INCORPORATION: ensures technical migration alignment with central criteria. | Monitoring

## Actions
Action ID | Parent Obligation ID | Action | Owner | Start Date | Due Date | Status | Percent Complete | Evidence Link | Notes
A-001 | OB-A11 | Publish a benchmarking exercise comparing NCC's contract exemption rates against neighbouring Nottinghamshire authorities. | A Spice / D Cafferty (Procurement) |  | 2026-07-31 | Not started | 0 |  | OB-A11.1 — Contract Procedure Rules Exemption Benchmarking. Evidence: formal benchmarking appendix in the Procurement Annual Report. Target: July 2026 Audit Committee.
A-002 | OB-A11 | Provide a clarification note splitting debt and investments between the General Fund and the Housing Revenue Account (HRA) in Table 5 of the Treasury Management Report. | Gareth Robinson (Director of Finance) | 2026-04-15 | 2026-06-30 | Complete | 100 | https://committee.nottinghamcity.gov.uk/documents/s178634/Appendix%2010_Treasury%20Management%20Strategy.pdf | OB-A11.2 — Treasury Management Table 5 Clarification. Evidence: signed addendum note or updated table in the finalised Treasury Management Strategy. Target: June 2026 Audit Committee.
A-003 | OB-A11 | Provide a formal briefing note once legal advice on UN PRI (Principles for Responsible Investment) and UNGP (UN Guiding Principles) compliance frameworks is received. | Beth Brown (Strategic Director of Legal and Governance) |  | 2026-06-30 | Not started | 0 |  | OB-A11.3 — UN PRI and UNGP Legal Briefing. Evidence: distributed legal briefing note; logged in committee minutes or correspondence record. Target: June 2026 Audit Committee.
A-004 | OB-L3 | Scope and procure the day-one IT systems and data migration required for the new unitary authority. | James Rhodes (Director of Policy, Performance and Communications) | 2026-06-01 | 2027-02-28 | Not started | 0 |  | Demonstrates the Part 9 cross-track financial gateway: this LGR action involves procurement / IT system migration, so the S151 sign-off note is attached automatically. ⚠️ Procurement/capital action: requires Section 151 sign-off under current spending controls before proceeding. Confirm with Stuart Fair or Gareth Robinson.
A-005 | OB-A10 | Prepare an Audit Committee briefing note on the LAO transition and its implications for NCC's PSAA-procured contract to 2027/28. | Gareth Robinson (Director of Finance) |  | 2026-09-30 | Not started | 0 |  | Supports OB-A10. Note Bill Butler as preferred LAO Chair candidate (May 2026).
A-006 | OB-A12 | Review structural transitional reporting regulations issued by the preferred LAO Chair candidate and adjust internal audit backstop clearance milestones accordingly. | Gareth Robinson (Director of Finance) | 2026-06-09 | 2026-09-30 | Not started | 0 |  | NEW ACTION: Leverages 8 June 2026 intelligence on Bill Butler's framework metrics.
A-007 | OB-L7 | Perform an internal option appraisal to cross-examine whether the newly introduced June 2026 GOV.UK reorganisation layout guidance changes boundary line migration costings. | James Rhodes (Director of Policy, Performance and Communications) | 2026-06-09 | 2026-08-31 | Not started | 0 |  | NEW ACTION: Triggered by 8 June 2026 GOV.UK Implementation Guidance paper updates.
A-008 | OB-L5 | Draft the formal accountability framework and code alignment overview mandated by the recent Royal Assent confirmation of the English Devolution Act. | Beth Brown (Strategic Director of Legal and Governance) | 2026-06-09 | 2026-07-31 | Not started | 0 |  | NEW ACTION: Directly links legislative confirmation of Act 2026 to the July 2026 Audit Committee agenda.
A-009 | OB-A2 | Coordinate final verification review and ensure physical sign-off endorsement of the complete CSIP text block by Ministerial Envoys. | Sajeeda Rose (Chief Executive) | 2026-06-05 | 2026-06-24 | In progress | 50 |  | NEW ACTION: Drives the immediate execution threshold for the statutory 3-month target deadline.