## Dashboard
NCC Audit Reform and LGR Obligations Tracker
Live status snapshot · Refreshed 04 August 2026
22 |  |  | 5 |  | 0 |  |  | 1
OBLIGATIONS |  |  | OVERDUE |  | DUE IN 30 DAYS |  |  | COMPLETE
OBLIGATIONS OVERVIEW
Obligations by Status |  |  |  | Obligations by Risk |  |  | Obligations by Theme
Status |  | Count |  | Risk Rating | Count |  | Theme |  | Count
Not started |  | 3 |  | High | 17 |  | Governance and Transparency |  | 9
In progress |  | 10 |  | Medium | 5 |  | LGR Transition |  | 7
Complete |  | 1 |  | Low | 0 |  | Financial Reporting |  | 3
Blocked |  | 0 |  |  |  |  | Audit Procurement |  | 2
Ongoing |  | 8 |  |  |  |  | Internal Controls |  | 1
ACTIONS & INTELLIGENCE FEED
Action Summary |  | Count |  | Intelligence Feed | Count
Total actions |  | 34 |  | Items captured | 208
In progress |  | 10 |  | Flagged material | 65
Complete |  | 1 |  | Material (last 30 days) | 35
Overdue |  | 7 |  | Awaiting review | 134
Avg. progress |  | 7%
Evidence coverage |  | 29% (10/34)
Evidence at completion |  | 100%
ATTENTION NEEDED
ID | Obligation |  |  |  |  | Owner |  |  | Target | Flag
OB-A2 | NCC must prepare and agree the Continuous Service Improvement Plan (CSIP) with the Ministerial Envoys within three months of the 24 March 2026 directions. |  |  |  |  | Sajeeda Rose (Chief Executive) |  |  | 24 Jun 2026 | Overdue
OB-A7 | NCC must respond to each recommendation in the external auditor's Annual Report and Audit Findings (ISA 260). |  |  |  |  | Gareth Robinson (Director of Finance) |  |  | 31 Jul 2026 | Overdue
OB-A9 | NCC must produce and publish an Annual Governance Statement reflecting the council's current governance position and any significant weaknesses. |  |  |  |  | Beth Brown (Strategic Director of Legal and Governance) |  |  | 31 Jul 2026 | Overdue
OB-A11 | NCC must progress the open items on the Audit Committee Recommendation Tracker through to completion (see linked actions OB-A11.1, .2, .3). |  |  |  |  | Kate Morris (Scrutiny and Audit Support Officer) |  |  | 31 Jul 2026 | Overdue
OB-L5 | NCC must review its governance, audit committee arrangements, and successor body governance in light of the English Devolution and Community Empowerment Act 20… |  |  |  |  | Beth Brown (Strategic Director of Legal and Governance) |  |  | 31 Jul 2026 | Overdue

## Intelligence
Date Found | Title | Source | Category | Published | Material | Matched | Theme | URL | Reviewed | Notes | Hash | Action Signal
2026-06-08 | Local Audit Office Chair: the government’s preferred candidate | GOV.UK | Correspondence | 2026-05-26 | Yes | Audit; Manually elevated - material legislative/appointment development (Audit) | Audit Procurement | https://www.gov.uk/government/publications/local-audit-office-chair-the-governments-preferred-candidate | Yes | Tracked as OB-A10 / OB-A12 (LAO transition alignment). | 29225ec1a415a81cf231e2c32c5a19de
2026-06-08 | Local government reorganisation: implementation guidance | GOV.UK | Guidance | 2026-05-21 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-implementation-guidance | Yes |  | 774a562d1fcbe994282fb838ddc67712
2026-06-08 | Local government reorganisation: Policy and programme updates | GOV.UK | Collection | 2026-03-12 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/collections/local-government-reorganisation-policy-and-programme-updates | Yes |  | 4d80bb6766cc36845f3aaa63ed38032e
2026-06-08 | Nottinghamshire and Nottingham: Local government reorganisation | GOV.UK | Guidance | 2026-02-05 | Yes | Local, Transition | LGR Transition | https://www.gov.uk/government/collections/nottinghamshire-and-nottingham-local-government-reorganisation | Yes |  | 438de41b33123f97381da2a9ae88434e
2026-06-08 | Local government reorganisation: summary of feedback on interim plans | GOV.UK | Guidance | 2025-06-03 | Yes | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-summary-of-feedback-on-interim-plans | Yes |  | f9370765871b9fce3681e7465d2c31d4
2026-06-08 | ​​English Devolution White Paper​: Power and partnership: Foundations for growth | GOV.UK | Guidance | 2024-12-16 | Yes | Transition; Manually elevated - material legislative/appointment development (LGR Transition / Audit) | LGR Transition | https://www.gov.uk/government/publications/english-devolution-white-paper-power-and-partnership-foundations-for-growth | Yes | Retained as foundational context for the 2026 Act; no separate obligation. | 95a642b258a7dc8e0061bfa8718344dc
2026-06-08 | Local government reorganisation: update on Secretary of State's decision regarding local elections of May 2026 | GOV.UK | Guidance | 2026-02-16 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-update-on-secretary-of-states-decision-regarding-local-elections-of-may-2026 | Yes |  | 8ef81633f5a750cb4c1ac14f8479b5df
2026-06-08 | Local government reorganisation: further letters to councils on local elections in May 2026 | GOV.UK | Guidance | 2026-01-29 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-further-letters-to-councils-on-local-elections-in-may-2026 | Yes |  | f0ca28d88494d6a9496f00f5172c71a1
2026-06-08 | ​​​Local government reorganisation: further letter to council leaders with elections in May 2026 | GOV.UK | Guidance | 2026-01-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-further-letter-to-council-leaders-with-elections-in-may-2026 | Yes |  | ebf079237d298efbcef8d2e05ff2e464
2026-06-08 | ​​​Local government reorganisation: letter to council leaders with elections in May 2026 | GOV.UK | Guidance | 2025-12-18 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-council-leaders-with-elections-in-may-2026 | Yes |  | c7adda5c60a04c17e302af0273366e2d
2026-06-08 | Local government reorganisation: letter to leaders on publicity code | GOV.UK | Guidance | 2025-11-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-leaders-on-publicity-code | Yes |  | 4fc0d66b0cbc7e1557ee2aa32833ef79
2026-06-08 | Local government reorganisation: letter to areas invited to submit final proposals | GOV.UK | Guidance | 2025-07-24 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals | Yes |  | 22d3f1b0d8f5579612f7cafd74384940
2026-06-08 | Local government reorganisation: letter to two-tier areas | GOV.UK | Guidance | 2025-01-15 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-two-tier-areas | Yes |  | 7dc6f9cdf34308af597518ba42239ab4
2026-06-08 | Local Government Reorganisation Advisory Group | GOV.UK | Guidance | 2026-05-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/groups/local-government-reorganisation-advisory-group | Yes |  | deb9b24ab99e8ba843c7fbc64c5e2ebb
2026-06-08 | Local government reorganisation in Nottinghamshire and Nottingham | GOV.UK | Guidance | 2026-02-05 | Yes | Local, Transition | LGR Transition | https://www.gov.uk/government/consultations/local-government-reorganisation-in-nottinghamshire-and-nottingham | Yes |  | 205848d9300953ace55c2f3f63b58552
2026-06-08 | Local government reorganisation: letter to council leaders | GOV.UK | Guidance | 2026-02-05 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-letter-to-council-leaders | Yes |  | b4fe184485e89661bc66c4738064cf08
2026-06-08 | Local audit reform | GOV.UK | Collection | 2025-12-02 | Unclear | Audit | Other | https://www.gov.uk/government/publications/local-audit-reform | Yes |  | 45fb6decc9967abb65dbfdbd6215b69b
2026-06-08 | Statutory intervention: Nottingham City Council | GOV.UK | Collection | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/collections/statutory-intervention-nottingham-city-council-minded-to-decision | Yes |  | c2dc55e3a57ff4e8f558291afcc1fc0b
2026-06-08 | Nottingham City Council: Letter to Chief Executive (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-chief-executive-24-march-2026 | Yes |  | 2898065a8f868eaa7fd43bbd82585e3c
2026-06-08 | Nottingham City Council: Ministerial Envoy appointment letter | GOV.UK | Guidance | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-envoy-appointment-letter | Yes |  | 2dbede6274db13509cc24e5283575c92
2026-06-08 | Nottingham City Council: Letter to former Commissioners (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-former-commissioners-24-march-2026 | Yes |  | 9fda66e1dc31a97df966b7bfb61d2152
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-24-march-2026 | Yes |  | 8035e4e92865a4e08aa53357659b4d9c
2026-06-08 | Nottingham City Council: Explanatory Memorandum (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-24-march-2026 | Yes |  | d3c467457b540a3f0bf614309aca9c19
2026-06-08 | Nottingham City Council: Representation (24 March 2026) | GOV.UK | Guidance | 2026-03-24 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation-24-march-2026 | Yes |  | 26fc51c10335d44f7a857673c0b0187d
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (4 February 2026) | GOV.UK | Guidance | 2026-02-04 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-4-february-2026 | Yes |  | 560ce0c0352c0e6f61e7726b7b64345b
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ fourth report | GOV.UK | Guidance | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-fourth-report | Yes |  | 600b6f4d89eb5413e08733526ceca1ed
2026-06-08 | Nottingham City Council: Commissioners’ fourth report | GOV.UK | Guidance | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-fourth-report | Yes |  | 99a0b5064ee8727c2347c9b72571b15b
2026-06-08 | Nottingham City Council: Explanatory Memorandum (updated 21 November 2025) | GOV.UK | Guidance | 2025-11-21 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-updated-21-november-2025 | Yes |  | 801a9c9285e4a5e78e6fc55a1359a162
2026-06-08 | Nottingham City Council: Commissioner appointment letters (updated 21 November 2025) | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioner-appointment-letters-updated-21-november-2025 | Yes |  | 6251f19915a405867e8db673d2d1d536
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ third report | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-third-report | Yes |  | 057d2e3166a08ecb5b94d555e58217d4
2026-06-08 | Nottingham City Council: Commissioners’ third report | GOV.UK | Guidance | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-third-report | Yes |  | 8c8111a055eaa3d14e02d4500ccb6cb3
2026-06-08 | Nottingham City Council: Ministerial response to the Commissioners’ second report | GOV.UK | Guidance | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-the-commissioners-second-report | Yes |  | cd73ff777fc694dab66f6b876a1c1c28
2026-06-08 | Nottingham City Council: Commissioners’ second report | GOV.UK | Guidance | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-second-report | Yes |  | d0c04d111712ea0ef8f01685db7108d2
2026-06-08 | Nottingham City Council: Exceptional Financial Support request 2025-26 | GOV.UK | Guidance | 2025-03-13 | Yes | Local, Intervention | Other | https://www.gov.uk/government/publications/nottingham-city-council-exceptional-financial-support-request-2025-26 | Yes |  | 5c4c10fa46b25394fc2cd21fe1c1d75f
2026-06-08 | Nottingham City Council: Ministerial response to Commissioners’ first report | GOV.UK | Guidance | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-response-to-commissioners-first-report | Yes |  | 71f2e56afb6d6753e35b172cc516b431
2026-06-08 | Nottingham City Council: Commissioners' first report | GOV.UK | Guidance | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioners-first-report | Yes |  | d98ca8e7ad028a097ebc6dda8f8e5aa3
2026-06-08 | Nottingham City Council Improvement and Assurance Board: final report | GOV.UK | Guidance | 2024-05-16 | Yes | Local | Internal Controls | https://www.gov.uk/government/publications/nottingham-city-council-improvement-and-assurance-board-final-report | Yes |  | b2a8fea237a904bd7678992fd8043a00
2026-06-08 | ​​Nottingham City Council: Explanatory Memorandum (updated 11 April 2024)​ | GOV.UK | Guidance | 2024-04-11 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-updated-11-april-2024 | Yes |  | b8cca80ece289181cd7b9f904d30f831
2026-06-08 | Nottingham City Council: Commissioner appointment letters | GOV.UK | Guidance | 2024-04-11 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-commissioner-appointment-letters-22-february-2024 | Yes |  | 3ca747b43d32cba56433c1fb3e64607a
2026-06-08 | Nottingham City Council: Exceptional Financial Support request 2024-25 | GOV.UK | Guidance | 2024-02-29 | Yes | Local, Intervention | Other | https://www.gov.uk/government/publications/nottingham-city-council-exceptional-financial-support-request-2024-25 | Yes |  | 0bb0ae6e9ccc3f81265482eab2db78a8
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-22-february-2024 | Yes |  | 17eeadd0b9d2a6883638b93980e8ae9f
2026-06-08 | Nottingham City Council: Ministerial letter to Sir Tony Redmond (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-letter-to-sir-tony-redmond-22-february-2024 | Yes |  | 2a180fc130afb8024014f66b839cde05
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-22-february-2024 | Yes |  | 145bba91104e4dbf70569b89dee1810a
2026-06-08 | Nottingham City Council: Explanatory Memorandum (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum-22-february-2024 | Yes |  | 10fde9f6a7ebdf4a7a5e61c0cda234b2
2026-06-08 | Nottingham City Council: Representation (22 February 2024) | GOV.UK | Guidance | 2024-02-22 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation-22-february-2024 | Yes |  | 05f81d6e412bec89bd864b13642d9780
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond (18 May 2023) | GOV.UK | Guidance | 2023-05-18 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond-18-may-2023 | Yes |  | 3024293ec6dec3a33dac3ca850b5b94e
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond (2 February 2023) | GOV.UK | Guidance | 2023-02-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond-2-february-2023 | Yes |  | af06ed33550e77fcda0f12683c985793
2026-06-08 | Nottingham City Council: Letter to the Chief Executive (2 September 2022) | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive-2-september-2022 | Yes |  | 2a1175d02720975b8afb24a6fb1fb0da
2026-06-08 | Nottingham City Council: Letter to Sir Tony Redmond | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-sir-tony-redmond | Yes |  | 33eef31789f3513e07cd9482e927715e
2026-06-08 | Nottingham City Council: Directions made under the Local Government Act 1999 (2 September 2022) | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-directions-made-under-the-local-government-act-1999-2-september-2022 | Yes |  | 3033603f989ae2332994a65f3ce3df47
2026-06-08 | Nottingham City Council: Explanatory Memorandum | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-explanatory-memorandum | Yes |  | a1b9b1e7a30adb3476c5cb6cbf61526c
2026-06-08 | Nottingham City Council: Representation | GOV.UK | Guidance | 2022-09-02 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-representation | Yes |  | 7774e32cabdf3f56996920439013a737
2026-06-08 | Nottingham City Council: Letter to the Chief Executive | GOV.UK | Guidance | 2022-06-23 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-the-chief-executive | Yes |  | d14b1f80d72f9a080f4127e336d3d554
2026-06-08 | Non-statutory review of Nottingham City Council | GOV.UK | Guidance | 2022-06-23 | Unclear | Local | Other | https://www.gov.uk/government/collections/non-statutory-review-of-nottingham-city-council | Yes |  | e512c646b828c631fbf72ad76fc7953a
2026-06-08 | English Devolution and Community Empowerment Act 2026 | Parliament | Bill |  | Yes | Transition; Manually elevated - material legislative/appointment development (LGR Transition / Audit) | LGR Transition | https://bills.parliament.uk/bills/4002 | Yes | Tracked as OB-L5 (governance gap analysis) and OB-A10 (LAO transition). | 2cc0140e559129309466a2e5502e619e
2026-06-08 | Bill Butler named as preferred candidate for Local Audit Office Chair | PSAA | PSAA Update | 2026-06-08 | Yes | Audit; Manually elevated - material legislative/appointment development (Audit) | Audit Procurement | https://www.psaa.co.uk/2026/05/bill-butler-named-as-preferred-candidate-for-local-audit-office-chair/ | Yes | Tracked as OB-A10 / OB-A12 (LAO transition alignment). | 217e8a844dbce9fac4bf4e2ffffd9c99
2026-06-08 | PSAA appoints Adrian Lythgo as new Board member | PSAA | PSAA Update | 2026-06-08 | Unclear | Audit | Audit Procurement | https://www.psaa.co.uk/2026/05/psaa-appoints-adrian-lythgo-as-new-board-member/ | Yes |  | 295e7fbfbe3919f6276fafbd7723ca11
2026-06-08 | English Devolution Bill receives Royal Assent | PSAA | PSAA Update | 2026-06-08 | Unclear | Transition | LGR Transition | https://www.psaa.co.uk/2026/04/english-devolution-bill-receives-royal-assent/ | Yes |  | ba312fc132d7eae858e78fe08546b660
2026-06-08 | Mayor joins partners as Nottingham launches bold City Vision | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/nottingham-city-vision/ | Yes |  | c02a3a1f32c99cbf8f89477289e4e686
2026-06-08 | Mayor welcomes Right to Request as 'devolution revolution' delivers for communities | EMCCA | Guidance |  | Unclear | Transition | LGR Transition | https://www.eastmidlands-cca.gov.uk/news/right-to-request/ | Yes |  | 55ae3f628fe09b311cad2563bb1a6772
2026-06-08 | Delight as Mayor helps open Nottingham's first major bridge over the Trent in almost 70 years | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/waterside-bridge-opens/ | Yes |  | c11a40c30dc7447bb458c4b1c001e5a7
2026-06-08 | Audit Committee — meeting 31 Jul 2026 9.30 am | NCC Committee | Committee Paper | 2026-07-31 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11775&Ver=4 | Yes |  | 9c81b083217b7e8f15e20e6550dcf8f7
2026-06-08 | Audit Committee — meeting 26 Jun 2026 9.30 am | NCC Committee | Committee Paper | 2026-06-26 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11601&Ver=4 | Yes |  | 988f05cdc883ae581691fd9dd43bc082
2026-06-08 | Audit Committee — meeting 27 Mar 2026 9.30 am | NCC Committee | Committee Paper | 2026-03-27 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11256&Ver=4 | Yes |  | 081e65a88e83aa5ca3c9e0aed7a2d2c3
2026-06-08 | Audit Committee — meeting 20 Feb 2026 9.30 am | NCC Committee | Committee Paper | 2026-02-20 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11255&Ver=4 | Yes |  | 7947dfbc1ac36c11ac3f5582a88d7f1a
2026-06-08 | Audit Committee — meeting 30 Jan 2026 9.30 am | NCC Committee | Committee Paper | 2026-01-30 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11477&Ver=4 | Yes |  | 8cbe63a69792be703749278df181fc09
2026-06-08 | Improvement Committee — meeting 26 Nov 2026 2.00 pm | NCC Committee | Committee Paper | 2026-11-26 | Yes | Local, Intervention | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=1175&MId=11731&Ver=4 | Yes |  | 1794f0fdfeb98b95d8b35be8cb10d0c4
2026-06-08 | Improvement Committee — meeting 4 Jun 2026 2.00 pm | NCC Committee | Committee Paper | 2026-06-04 | Yes | Local, Intervention | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=1175&MId=11730&Ver=4 | Yes |  | 996fb9ef9e75bca4bdbe62e7bfa5d568
2026-07-21 | Local government reorganisation: decision letter to Nottinghamshire and Nottingham council leaders | GOV.UK | Guidance | 2026-07-16 | Yes | Local, Intervention, Transition | Governance and Transparency; LGR Transition | https://assets.publishing.service.gov.uk/media/6a58d3105ca06bf11ccb42f9/Local_government_reorganisation_-_decision_letter_to_Nottinghamshire_and_Nottingham_council_leaders.pdf | Yes |  | 922aff122e53aa39c6b3a55c40b522e7 | Possible obligation (Produce)
2026-07-21 | Local Government Reorganisation: Nottinghamshire and Nottingham (HCWS286 written ministerial statement) | Parliament | Written Statement | 2026-07-16 | Yes | Local, Intervention, Transition | Governance and Transparency; LGR Transition | https://questions-statements.parliament.uk/written-statements/detail/2026-07-16/hcws286 |  |  | 1d8ab81c3bfc61ea7fc7d6a6b85fc6c3
2026-08-04 | Local audit reform: a strategy for overhauling the local audit system in England | GOV.UK | Guidance | 2025-04-09 | Unclear | Audit | Other | https://www.gov.uk/government/consultations/local-audit-reform-a-strategy-for-overhauling-the-local-audit-system-in-england |  |  | 1e50fd52139280b50193981c1ba379b0
2026-08-04 | Overhaul of local audit will restore trust in broken system | GOV.UK | News | 2025-04-09 | Unclear | Audit | Other | https://www.gov.uk/government/news/overhaul-of-local-audit-will-restore-trust-in-broken-system |  |  | 595b8a1f7de7752984dfe92a59f54894
2026-08-04 | Significant measures to tackle worsening backlog in local audit | GOV.UK | News | 2024-07-31 | Unclear | Audit | Other | https://www.gov.uk/government/news/significant-measures-to-tackle-worsening-backlog-in-local-audit |  |  | 09af165bcc3e16220f2556e5eac75d06
2026-08-04 | English Devolution and Community Empowerment Bill​: Guidance | GOV.UK | Guidance | 2025-12-03 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-guidance |  |  | 16b9e2e8c7ceba6ecc3c638046c17851
2026-08-04 | Addressing the local audit backlog in England: Consultation | GOV.UK | Guidance | 2024-09-09 | Unclear | Audit | Other | https://www.gov.uk/government/consultations/addressing-the-local-audit-backlog-in-england-consultation |  |  | 279e71bf26b79d07a9933620d57a4d83
2026-08-04 | Lessons learnt from best value interventions 2025 | GOV.UK | Guidance | 2026-03-19 | Unclear | Intervention | Governance and Transparency | https://www.gov.uk/government/publications/lessons-learnt-from-best-value-interventions-2025 |  |  | a77b9642ac9e627208a1772ec5998775
2026-08-04 | Local Audit Office | GOV.UK | Guidance | 2026-06-22 | Unclear | Audit | Audit Procurement | https://www.gov.uk/government/organisations/local-audit-office |  |  | 3eba031140dc72f1ae9b6ac98e647e4c
2026-08-04 | Local Audit Office chair: appointment | GOV.UK | Correspondence | 2026-07-01 | Unclear | Audit | Audit Procurement | https://www.gov.uk/government/publications/local-audit-office-chair-appointment |  |  | 294ef69ec5d17b913c08f8082856d47d
2026-08-04 | Addressing the local audit backlog in England: Non-compliance lists | GOV.UK | Report | 2026-03-26 | Unclear | Audit | Financial Reporting | https://www.gov.uk/government/publications/addressing-the-local-audit-backlog-in-england-non-compliance-lists |  |  | db9c28badc4bf466701e6683e8aecaa5
2026-08-04 | Audit build-back grant 2024 to 2025: technical note | GOV.UK | Guidance | 2026-01-06 | Unclear | Audit | Financial Reporting; Internal Controls | https://www.gov.uk/government/publications/audit-build-back-grant-2024-to-2025-technical-note |  |  | db8fd40e6261bece0591fd6498698a6e
2026-08-04 | Addressing the local audit backlog: modified or disclaimed audit opinions | GOV.UK | Guidance | 2024-11-27 | Unclear | Audit | Other | https://www.gov.uk/government/publications/addressing-the-local-audit-backlog-modified-or-disclaimed-audit-opinions |  |  | c572e48d8239344b00d316e2a34fb21e
2026-08-04 | Plan-making and local government reorganisation | GOV.UK | Guidance | 2026-07-06 | Unclear | Transition | LGR Transition | https://www.gov.uk/guidance/plan-making-and-local-government-reorganisation |  |  | 1b7951e7c4e2df1dc78646934093d82b
2026-08-04 | Local government reorganisation: staffing issues guidance | GOV.UK | Guidance | 2026-07-16 | Yes | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-staffing-issues-guidance | Yes | REVIEWER OVERRIDE: auto-scored Unclear (title matches Transition only, does not name Nottingham). Judged material by review. Non-statutory MHCLG guidance (16 Jul 2026, overview PDF added 30 Jul) on appointment and transfer of employees to new single-tier councils. Bears on OB-L1 day-one transition and on A-023 HR operating-model work. Tracked via A-025 and A-026. | e03687434a9f6ff2bd10efccad59e4ee
2026-08-04 | Local government reorganisation: guidance on sector support | GOV.UK | Guidance | 2026-07-16 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-guidance-on-sector-support |  |  | 079aa32d39a3c253672b49a9b9115fca
2026-08-04 | Local Government Pension Scheme administering authorities: local government reorganisation | GOV.UK | Guidance | 2026-07-30 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-pension-scheme-administering-authorities-local-government-reorganisation |  |  | 2f8d70b7509f53dbfd93934bc4bda539
2026-08-04 | Local government reorganisation: implementation letters to council chief executives | GOV.UK | Correspondence | 2026-07-19 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-implementation-letters-to-council-chief-executives |  |  | 35548d7dca67af2b3c68a8f6424f960f
2026-08-04 | Local government reorganisation: implementation letter to Nottinghamshire and Nottingham chief executives | GOV.UK | Correspondence | 2026-07-29 | Yes | Local, Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-implementation-letter-to-nottinghamshire-and-nottingham-chief-executives |  |  | b575f8401a24a4c352800aed621914c3
2026-08-04 | Local government reorganisation: decision letters to council leaders | GOV.UK | Correspondence | 2026-07-16 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/local-government-reorganisation-decision-letters-to-council-leaders |  |  | 000ecc83caf10cfb692d24b886f3ad2c
2026-08-04 | English Devolution and Community Empowerment Bill | GOV.UK | Guidance | 2025-07-09 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/collections/english-devolution-and-community-empowerment-bill |  |  | 6b7abc0e2ce54f1af28d0306b0ac561d
2026-08-04 | English Devolution and Community Empowerment Bill: European Convention on Human Rights Memorandum | GOV.UK | Guidance | 2025-11-27 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-european-convention-on-human-rights-memorandum |  |  | b2048dae4dd6782b1696ea33a681b21b
2026-08-04 | RPC opinion: English Devolution and Community Empowerment Bill impact assessment | GOV.UK | Guidance | 2025-07-09 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-bill-ia-rpc-opinion-green-rated |  |  | feeff1a3acec4f4561ec027af42d195b
2026-08-04 | English Devolution and Community Empowerment Bill: Impact assessment | GOV.UK | Guidance | 2025-11-27 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-impact-assessment |  |  | 7ddcd6a35f7ba1fd60d15bc1559ca384
2026-08-04 | New amendments will create safer streets, champion culture, and strengthen local accountability under the English Devolution Bill | GOV.UK | News | 2026-03-18 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/new-amendments-will-create-safer-streets-champion-culture-and-strengthen-local-accountability-under-the-english-devolution-bill |  |  | 03de3cfd30b036e09728af42e9f02957
2026-08-04 | English Devolution Bill receives Royal Assent | GOV.UK | News | 2026-04-29 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/english-devolution-bill-receives-royal-assent |  |  | bc86516e9db09c52b0b5676c897fe904
2026-08-04 | Landmark Devolution Bill brings new dawn of regional power | GOV.UK | News | 2025-07-10 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/landmark-devolution-bill-brings-new-dawn-of-regional-power |  |  | 4bd0a75b22b3e24b04e0d8830c6ce8d5
2026-08-04 | English rail devolution applications | GOV.UK | Guidance | 2025-12-12 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-rail-devolution-applications |  |  | adfe9c8ae92657439a711caee71b503b
2026-08-04 | ​English devolution: Area factsheets | GOV.UK | Guidance | 2025-07-09 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-area-factsheets |  |  | 16b529eb2c68fac4023c1c5b7547eac5
2026-08-04 | Devolution: Guidance for civil servants | GOV.UK | Guidance | 2025-11-28 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/devolution-guidance-for-civil-servants |  |  | 69e94c82bb7262492b1166974bc53853
2026-08-04 | Appointing mayoral commissioners and setting/reporting allowances | GOV.UK | Guidance | 2026-08-03 | Unclear | Intervention | Governance and Transparency | https://www.gov.uk/government/publications/appointing-mayoral-commissioners-and-settingreporting-allowances |  |  | 462ff4607cc2059382b67b8966f250e0
2026-08-04 | Full steam ahead for Devolution Priority Programme | GOV.UK | News | 2025-07-17 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/full-steam-ahead-for-devolution-priority-programme |  |  | d2bba07fd13bb80ffda441e2579bb23b
2026-08-04 | Devolution Priority Programme consultations launch | GOV.UK | News | 2025-02-17 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/devolution-priority-programme-consultations-launch |  |  | 81aa312e4e639dc7a344ac5b7fecbb64
2026-08-04 | ‘Devolution Revolution’ forges ahead with more powers for Mayors | GOV.UK | News | 2024-12-16 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/devolution-revolution-forges-ahead-with-more-powers-for-mayors |  |  | 6aac9e382f8aae640e01a2fef0ca16b1
2026-08-04 | Devolution revolution: six areas to elect Mayors for first time | GOV.UK | News | 2025-02-05 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/devolution-revolution-six-areas-to-elect-mayors-for-first-time |  |  | fc79533439b43245580512fdeecdf54d
2026-08-04 | Full devolution to be delivered across the North | GOV.UK | News | 2024-09-22 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/full-devolution-to-be-delivered-across-the-north |  |  | 9c090cea0b763c8187f29d902554003d
2026-08-04 | Four devolution agreements signed off and others progressing | GOV.UK | News | 2024-09-21 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/news/four-devolution-agreements-signed-off-and-others-progressing |  |  | 4b07c22dbedae948182a25e6c39ae3a2
2026-08-04 | ​​Annual report on English devolution 2024 to 2025​ | GOV.UK | Guidance | 2025-10-13 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/annual-report-on-english-devolution-2024-to-2025 |  |  | 48b876d55dc1cc92a82ce0497a683f12
2026-08-04 | Exceptional Financial Support for local authorities | GOV.UK | Guidance | 2026-02-23 | Unclear | Intervention | Other | https://www.gov.uk/government/collections/exceptional-financial-support-for-local-authorities |  |  | 0fb85b6aaedbac622cb7e7248876dc95
2026-08-04 | Exceptional Financial Support for local authorities for 2026-27 | GOV.UK | Guidance | 2026-07-30 | Unclear | Intervention | Other | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2026-27 |  |  | 9d3c8b97e605b22160e529e68d610a2e
2026-08-04 | Exceptional Financial Support for local authorities for 2025-26 | GOV.UK | Guidance | 2026-02-23 | Unclear | Intervention | Other | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2025-26 |  |  | 5a9ce004d66d138fa56363fa6200228d
2026-08-04 | Exceptional Financial Support for local authorities for 2024-25 | GOV.UK | Guidance | 2026-03-05 | Unclear | Intervention | Internal Controls | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2024-25 |  |  | ae9e7b85111f3e9a3cc74d08a316b0b0
2026-08-04 | Exceptional Financial Support for local authorities for 2021-22 | GOV.UK | Guidance | 2025-03-13 | Unclear | Intervention | Internal Controls | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2021-22 |  |  | d9f3286330b2e72aabcd30a7647f8676
2026-08-04 | Exceptional Financial Support for local authorities for 2023-24 | GOV.UK | Guidance | 2026-03-05 | Unclear | Intervention | Internal Controls | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2023-24 |  |  | 9319ef296a9398e4e0787e6af324183a
2026-08-04 | Exceptional Financial Support for local authorities for 2022-23 | GOV.UK | Guidance | 2026-02-23 | Unclear | Intervention | Internal Controls | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2022-23 |  |  | b0a0c8718216252667569dbcd4c45ed0
2026-08-04 | Exceptional Financial Support for local authorities for 2020-21 | GOV.UK | Guidance | 2025-03-13 | Unclear | Intervention | Internal Controls | https://www.gov.uk/guidance/exceptional-financial-support-for-local-authorities-for-2020-21 |  |  | 7ce4a135ce589d9207596d3f670faa03
2026-08-04 | Nottingham City Council: Ministerial Envoy appointment letter (24 March 2026) | GOV.UK | Correspondence | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-envoy-appointment-letter |  |  | 9dba86372ea855b346eee5e8dab59210
2026-08-04 | Nottingham City Council: Ministerial Envoy appointment letter (15 July 2026) | GOV.UK | Correspondence | 2026-07-15 | Yes | Local, Intervention | Governance and Transparency | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-envoy-appointment-letter-15-july-2026 |  |  | 62576f7ad2e8cd21beb061a27f1c57ac
2026-08-04 | Nottingham City Council: Letter to Council Leader (15 July 2026) | GOV.UK | Guidance | 2026-07-15 | Unclear | Local | Other | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-council-leader-15-july-2026 |  |  | 4d2789f8d6fb3b189b31ccb5ec755afa
2026-08-04 | Press release: Bill Butler confirmed as Chair of the Local Audit Office | PSAA | PSAA Update | 2026-08-04 | Unclear | Audit | Audit Procurement | https://www.psaa.co.uk/2026/07/press-release-bill-butler-confirmed-as-chair-of-the-local-audit-office/ |  |  | 7b681eccadf0ba6e478b71f22770eaf2
2026-08-04 | MHCLG seeks Controller of Local Audit | PSAA | PSAA Update | 2026-08-04 | Unclear | Audit | Other | https://www.psaa.co.uk/2026/06/mhclg-seeks-controller-of-local-audit/ |  |  | 0461b2bedc620cd6c2181f308b2424d3
2026-08-04 | East Midlands Combined County Authority granted Established Status by government | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/established-status-2026/ |  |  | 7659f2966da8a6bdff612209d753fb37
2026-08-04 | Mayor Claire invests £7 million to deliver neighbourhood improvements across Nottingham | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/nottingham-neighbourhood-improvements/ |  |  | 1fb78d09dac2bb557eaf2053c6840717
2026-08-04 | Mayor-backed £12.6m investment helps drive forward A614/A6097 improvements in Nottinghamshire | EMCCA | Guidance |  | Unclear | Local | Other | https://www.eastmidlands-cca.gov.uk/news/a614-works-nottinghamshire/ |  |  | ae9743d4cef5947a9b92231a2aa845e0
2026-08-04 | Audit Committee — meeting 27 Nov 2026 9.30 am | NCC Committee | Committee Paper | 2026-11-27 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11777&Ver=4 |  |  | 4e29488c8ccd2d206e77d02118ba9fec
2026-08-04 | Audit Committee — meeting 25 Sep 2026 9.30 am | NCC Committee | Committee Paper | 2026-09-25 | Yes | Local, Audit | Governance and Transparency | https://committee.nottinghamcity.gov.uk/ieListDocuments.aspx?CId=145&MId=11776&Ver=4 |  |  | f3f3ea6b369cef28e63497e6f1127c32
2026-08-04 | English Devolution and Community Empowerment Act 2026 | legislation.gov.uk | Act | 2026-05-11 | Yes | Audit, Transition | Governance and Transparency; LGR Transition | https://www.legislation.gov.uk/id/ukpga/2026/23 |  |  | f25d6de2a294b13dfbfa8f6c3330fd0e
2026-08-04 | The English Devolution and Community Empowerment Act 2026 (Commencement No. 2) Regulations 2026 | legislation.gov.uk | Statutory Instrument | 2026-07-16 | Yes | Audit, Transition | Governance and Transparency; LGR Transition | https://www.legislation.gov.uk/id/uksi/2026/812 | Yes | Commenced s.94 (audit committees) of the EDCEA 2026 for Category 1 authorities from 15 July 2026, inserting s.33A into the Local Audit and Accountability Act 2014. Notified to S151 Officers by MHCLG letter of 31 July 2026 (not published on GOV.UK). Creates OB-A13; tracked via A-027, A-028 and A-029. | e3b1fa53dde80e03f7970343151e8ca9
2026-08-04 | The English Devolution and Community Empowerment Act 2026 (Commencement No. 1 and Saving) Regulations 2026 | legislation.gov.uk | Statutory Instrument | 2026-06-17 | Yes | Audit, Transition | Governance and Transparency; LGR Transition | https://www.legislation.gov.uk/id/uksi/2026/656 |  |  | 254484ad362d50bf093d83a43e2c458d
2026-08-04 | The English Devolution and Community Empowerment Act 2026 (Consequential Amendments and Revocations) (England) Regulations 2026 | legislation.gov.uk | Statutory Instrument | 2026-05-14 | Yes | Audit, Transition | Governance and Transparency; LGR Transition | https://www.legislation.gov.uk/id/uksi/2026/519 |  |  | 27c41f4a3b1de29927a3a8b3533cd42d
2026-08-04 | The English Devolution and Community Empowerment Act 2026 (Transitional and Saving Provisions) (England) Regulations 2026 | legislation.gov.uk | Statutory Instrument | 2026-06-26 | Yes | Audit, Transition | Governance and Transparency; LGR Transition | https://www.legislation.gov.uk/id/uksi/2026/482 |  |  | 9180d0ef6e4d4904245d7efd27f8af77
2026-08-04 | English Devolution and Community Empowerment Act 2026​: Devolution Framework Explainers | GOV.UK | Collection | 2026-06-08 | Unclear | Transition | LGR Transition | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-devolution-framework-explainers | Yes | REVIEWED: sets out statutory functions of STRATEGIC AUTHORITIES (EMCCA), not a duty on NCC directly. Matters because it defines the EMCCA / unitary boundary for day-one service allocation. Tracked as OB-L8 and A-033. | 793b25e65048d4f116057d15abe114de
2026-08-04 | Local Government Pension Scheme administering authorities: local government reorganisation | GOV.UK | Attachment | 2026-07-30 | Unclear | Transition | LGR Transition | /government/publications/local-government-pension-scheme-administering-authorities-local-government-reorganisation/local-government-pension-scheme-administering-authorities-local-government-reorganisation |  |  | db64c6563818b46ba1012f37a74edecb
2026-08-04 | Local government reorganisation: staffing issues guidance | GOV.UK | Attachment | 2026-07-16 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a58f75b24d4d0ad06d94627/LGR_Staffing_Issues_Guidance.pdf |  |  | f39506aa245d02927dd42bbdfe0310b6
2026-08-04 | Local government reorganisation: staffing issues guidance overview | GOV.UK | Attachment | 2026-07-16 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a58d69b908b618a53702f04/Local_government_reorganisation_-_staffing_issues_guidance_overview.pdf |  |  | 86d92d34bceef52fe5b627fff74051a0
2026-08-04 | Local government reorganisation: guidance on sector support | GOV.UK | Attachment | 2026-07-16 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a58a7452f6185941a9a6647/Local_government_reorganisation_-_sector_support_guidance.pdf |  |  | eabdca899e75b10c3f91ee83057bae71
2026-08-04 | Local government reorganisation: implementation guidance for the first transition period | GOV.UK | Attachment | 2026-05-21 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/69b1a416cdd628b29e349705/Local_government_reorganisation_-_implementation_guidance.pdf |  |  | bbb4a9c71e2ea227048901ed55969917
2026-08-04 | Local government reorganisation: implementation guidance for the second transition period | GOV.UK | Attachment | 2026-05-21 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a0eeefc9c0df135284ec7ae/Local_government_reorganisation_-_implementation_guidance_for_the_second_transition_period.pdf |  |  | 54c000e984637d9b46caaed5e0b2958b
2026-08-04 | Local government reorganisation: summary of feedback on interim plans | GOV.UK | Attachment | 2025-06-03 | Unclear | Transition | LGR Transition | /government/publications/local-government-reorganisation-summary-of-feedback-on-interim-plans/local-government-reorganisation-summary-of-feedback-on-interim-plans |  |  | 81eb402569d1df2510c023e510b7e5fd
2026-08-04 | English Devolution White Paper | GOV.UK | Attachment | 2024-12-16 | Unclear | Transition | LGR Transition | /government/publications/english-devolution-white-paper-power-and-partnership-foundations-for-growth/english-devolution-white-paper |  |  | 09e260469495b3c018781499a703a588
2026-08-04 | English Devolution White Paper | GOV.UK | Attachment | 2024-12-16 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/67ade9866e6c8d18118acd58/English_Devolution_White_Paper_Web_Accessible.pdf |  |  | f4510012e08feda08cae1d99ad3df59e
2026-08-04 | Letter to council leaders: update on Secretary of State's decision regarding local elections of May 2026 | GOV.UK | Attachment | 2026-02-16 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/699328da7da91680ad7f44a9/update_on_secretary_of_state_s_decision_regarding_local_elections_of_may_2026_-_letter_to_council_leaders.pdf |  |  | 3c86e7aa79ba15032b729f3217637941
2026-08-04 | Letter to Pendle Borough Council | GOV.UK | Attachment | 2026-01-29 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/697b3799b28b2cc262572ef3/Letter_to_Pendle_Borough_Council.pdf |  |  | c02ac374d257069f0ea849fa80219338
2026-08-04 | Letter to council leaders on the postponement of May 2026 local elections | GOV.UK | Attachment | 2026-01-22 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/69720b4ca1311bdcfa0ed8ab/Letter_to_Council_Leaders_on_postponement_of_local_elections_in_May_2026.pdf |  |  | 7f5b1249783a65c2e3ee3ba440afa0fd
2026-08-04 | Letter to leader of Oxford City Council | GOV.UK | Attachment | 2026-01-19 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/696e1a4f091f0cc41e81a24b/Letter_to_leader_of_Oxford_City_Council.pdf |  |  | 2524783ce18e0a6978e2c132a8b17d02
2026-08-04 | Letter to leader of Southampton City Council | GOV.UK | Attachment | 2026-01-19 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/696e1a9da426b80193afc7fe/Letter_to_leader_of_Southampton_City_Council.pdf |  |  | 1b163337356b2ca5ac74cb2f58ec8df6
2026-08-04 | Letter to council leaders with elections in May 2026 | GOV.UK | Attachment | 2025-12-18 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6944196136f089d38be1f31a/lgr-letter-councils-elections-may-2026.pdf |  |  | e4f385faea14eb07dd43377a034ae032
2026-08-04 | Letter to council leader on the publicity code | GOV.UK | Attachment | 2025-11-19 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/691dde2f513046b952c500af/Letter_to_Leaders_on_Publicity_Code_and_Local_Government_Reorganisation.pdf |  |  | 9b8895f9a5e3963b18c575962e3b9050
2026-08-04 | Local government reorganisation: letter to areas invited to submit final proposals | GOV.UK | Attachment | 2025-07-24 | Unclear | Transition | LGR Transition | /government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals |  |  | 2bded096ec6af781c7ec3e4d20e236bc
2026-08-04 | Local government reorganisation: Considerations for partnership working in social care for new unitary authorities | GOV.UK | Attachment | 2025-07-24 | Unclear | Transition | LGR Transition | /government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals/local-government-reorganisation-considerations-for-partnership-working-in-social-care-for-new-unitary-authorities |  |  | 88dbe6cf11d66c4e37fd7908b3f74466
2026-08-04 | Summary of the local government reorganisation process | GOV.UK | Attachment | 2025-07-24 | Unclear | Transition | LGR Transition | /government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals/summary-of-the-local-government-reorganisation-process |  |  | 363996639d432ab1f1b8904a0c3ecd02
2026-08-04 | Financial decisions before local government reorganisation | GOV.UK | Attachment | 2025-07-24 | Unclear | Transition | LGR Transition | /government/publications/local-government-reorganisation-letter-to-areas-invited-to-submitted-final-proposals/financial-decisions-before-local-government-reorganisation |  |  | 6a4a8336d5645c502d3fd8326204efa5
2026-08-04 | Nottinghamshire and Nottingham | GOV.UK | Attachment | 2025-02-06 | Yes | Local, Transition | LGR Transition | /government/publications/local-government-reorganisation-invitation-to-local-authorities-in-two-tier-areas/nottinghamshire-and-nottingham |  |  | f2077f587d88ce4ffdbe198a8e816e98
2026-08-04 | Letter from Jim McMahon, Minister for Local Government and English Devolution (16 December 2024) | GOV.UK | Attachment | 2025-01-15 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/67864788f041702a11ca0f44/Local_government_reorganisation_-_letter_to_two-tier_areas.pdf |  |  | bf0f43be0abe9545716d6f8155796eaf
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 12 May 2025 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/68834b9ebe2291b14d11aee6/Local_Government_Reorganisation_Advisory_Group_12_May_2025.pdf |  |  | 71554a1fad9a19e033a4581981496e2f
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 3 September 2025 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/690386535c84b1206832a89c/LGR_Advisory_Group_Meeting_Summary_3_September.pdf |  |  | 5bb4038044a04e13d53345d49f83eabb
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 6 October 2025 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/690386695c84b1206832a89d/October_Advisory_Group_Short_Summary.pdf |  |  | d68e5618875880643c4a5820f54f2388
2026-08-04 | Local Government Reorganisation Advisory Group – Terms of Reference and membership | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/690387655c84b1206832a89e/LGR_AG_Terms_of_Reference_and_membership.pdf |  |  | 41e699f0548aef37fb1ff772c0247d00
2026-08-04 | Local Government Reorganisation Advisory Group 6 November 2025 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/697cc7a7edc921ef1a245284/Local_Government_Reorganisation__LGR__Advisory_Group__November_6_2025.pdf |  |  | cebb010c1e2ec0e1db39779bb8ed6a0a
2026-08-04 | Local Government Reorganisation Advisory Group 4 December 2025 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/697cc85f3915f7123658004d/Local_Government_Reorganisation_Advisory_Group_4_December_2025.pdf |  |  | 4bb6970b6bd45aa2abeaa1c1c99034f4
2026-08-04 | Local Government Reorganisation Advisory Group 13 January 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/697cc95084f2153b11245288/Local_Government_Reorganisation_Advisory_Group_13_January_2026.pdf |  |  | 80d720500b4dd5ea7e56924c2f842b3e
2026-08-04 | Local Government Reorganisation Advisory Group 12 February 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/699ecf713e672177d0bc762d/20260217_LGRAG_February_Meeting_Short_Summary__1_.pdf |  |  | d39e13b8901cfd1bfa4a371e0f6b9047
2026-08-04 | Local Government Reorganisation Advisory Group 18 March 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/69ccfcf1b5210036050bc5f1/Local_government_reorganisation_advisory_group_meeting_summary_18_March_2026.pdf |  |  | 3e06834ec6a43ab6c7fec9c70e0cf656
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 16 April 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/69e8ca77d36883a64473b838/20260416_LGRAG_April_Meeting_Short_Summary_.pdf |  |  | 9704d74351bd5e684f579fb559388c20
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 12 May 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a0c3c7afcae986635db919b/LGRAG_May_Meeting_Short_Summary.pdf |  |  | 9e825e676176ab3df7c2241d05e6708b
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 11 June 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a621cbce2d191f0bc8b6de6/LGRAG_June_Meeting_Short_Summary.pdf |  |  | f5b78258b271ad80e9922201c9792676
2026-08-04 | Local Government Reorganisation (LGR) Advisory Group 23 July 2026 | GOV.UK | Attachment | 2026-08-04 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a71bbe9dc689ac736a4766e/Local_government_reorganisation_advisory_group_meeting_summary_23_July_2026.pdf |  |  | b5a1bd87d323af69c2f074e01e1ae997
2026-08-04 | Proposals for local government reorganisation in Nottinghamshire and Nottingham | GOV.UK | Attachment | 2026-07-22 | Yes | Local, Transition | LGR Transition | /government/consultations/local-government-reorganisation-in-nottinghamshire-and-nottingham/proposals-for-local-government-reorganisation-in-nottinghamshire-and-nottingham |  |  | 1bc824c674f2b76bbd6ba50f18b5f21e
2026-08-04 | Nottinghamshire and Nottingham: Summary and analysis of consultation responses | GOV.UK | Attachment | 2026-07-22 | Yes | Local, Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a60a25534dfb74772f96d06/Nottinghamshire_and_Nottingham_-_Summary_and_analysis_of_consultation_responses.pdf |  |  | e221487734bf2a83726fb1c13475f6eb
2026-08-04 | Local government reorganisation: implementation letter to Nottinghamshire and Nottingham chief executives | GOV.UK | Attachment | 2026-07-29 | Yes | Local, Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a6a10ada95350305084f78b/Local_government_reorganisation_-_implementation_letter_to_Nottinghamshire_and_Nottingham_chief_executives.pdf |  |  | 38f9b366fa9fcb3b82d7b0f9a3d54865
2026-08-04 | Letter to Council Leaders | GOV.UK | Attachment | 2026-02-05 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/69848c0f2df808759a7bd712/Letter_to_Council_Leaders_5_February_2026.pdf |  |  | b8613cbf9ef267df427e650bf47b9cbd
2026-08-04 | Local Audit Transition Plan | GOV.UK | Attachment | 2025-12-02 | Unclear | Audit | Other | https://assets.publishing.service.gov.uk/media/6926f871345e31ab14ecf524/Local_Audit_Transition_Plan.pdf | Yes | REVIEWED: MHCLG, Nov 2025. Annex A carries the LAO milestone timeline. Corrects OB-A10 — PSAA contracts with audit firms extended to 2030, not 2027/28. Auditor appointment and contracting duties transfer to the LAO Spring 2027. Confirms the statutory audit committee requirement behind OB-A13 and the SoS power to issue statutory guidance behind A-029. | ec93a5ad87c1fcbe3dfba567356b9f19
2026-08-04 | Ministerial letter to audit firms | GOV.UK | Attachment | 2025-12-02 | Unclear | Audit | Other | https://assets.publishing.service.gov.uk/media/692992bf9c1eda2cdf03429c/Ministerial_letter_to_local_audit_firms.pdf |  |  | 4b5a932c3b2d0c295d0e28fb608b6a10
2026-08-04 | Ministerial letter to local bodies | GOV.UK | Attachment | 2025-12-02 | Unclear | Audit | Other | https://assets.publishing.service.gov.uk/media/692992e6a245b0985f034280/Ministerial_letter_to_local_bodies.pdf | Yes | REVIEWED: Alison McGovern MP to Chief Executives, CFOs and Leaders, 27 Nov 2025. Asks authorities to permit their auditor to share the Auditor Annual Report and ISA 260 with MHCLG by 31 Mar 2026, and a capacity assessment by end Jul 2026 — BOTH DATES NOW PASSED, needs a retrospective check that NCC responded. Backstop for clearing disclaimers is 30 Nov 2028. No further build-back grant in 2025/26. | 2c4d9bf5ca20effcf72f58d6dd35b446
2026-08-04 | Devolution Framework Explainer: Established Mayoral Strategic Authorities | GOV.UK | Attachment | 2026-06-08 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a26d62c8e85b4e5346ac0e2/Devolution_Framework_Explainer_-_Established_Mayoral_Strategic_Authorities.pdf |  |  | 77f308678d96d12c59d3c6de5aee6058
2026-08-04 | Devolution Framework Explainer: Mayoral Strategic Authorities | GOV.UK | Attachment | 2026-06-08 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a26d63b56960b0542c0b1bf/Devolution_Framework_Explainer_-_Mayoral_Strategic_Authorities.pdf |  |  | e949d04c576c4e340e3aa3380dfb1bf6
2026-08-04 | Devolution Framework Explainer: Non-Mayoral Foundation Strategic Authorities | GOV.UK | Attachment | 2026-06-08 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a26d6498e85b4e5346ac0e3/Devolution_Framework_Explainer_-_Non-Mayoral_Foundation_Strategic_Authorities.pdf |  |  | 63ea6abaf72e003caaa30e6bc86885dc
2026-08-04 | Devolution Framework Explainer: Single Local Authority Foundation Strategic Authorities | GOV.UK | Attachment | 2026-06-08 | Unclear | Transition | LGR Transition | https://assets.publishing.service.gov.uk/media/6a26d657f56856fd11c0b19a/Devolution_Framework_Explainer_-_Single_Local_Authority_Foundation_Strategic_Authorities.pdf |  |  | 52d602a87f08289fc5d853450f09deb5
2026-08-04 | Nottingham City Council: Letter to Council Leader (15 July 2026) | GOV.UK | Attachment | 2026-07-15 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/6a5759d19e631544544136cd/Nottingham_Minister_letter_to_Leader_of_the_Council_-_July_2026.pdf |  |  | 7a5f34b199f0d96f9b51d9efcd859604
2026-08-04 | Nottingham City Council: Ministerial Envoy appointment letter (15 July 2026) | GOV.UK | Attachment | 2026-07-15 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/6a574b882cbe5d1c179a6500/Sir_Steve_Houghton_Nottingham_appointment_letter_-_July_2026.pdf |  |  | 2a0b875692191cb25f4eeda0d92f644e
2026-08-04 | Nottingham City Council: Letter to Chief Executive (24 March 2026) | GOV.UK | Attachment | 2026-03-24 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/69c14cedbb0dfe55b83e4ba4/Nottingham_James_Blythe_Letter_to_Chief_Executive.pdf |  |  | 8f1247a4f902928d0ea99043bb50d75d
2026-08-04 | Nottingham City Council: Ministerial Envoy appointment letter | GOV.UK | Attachment | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/69c14b1313101e9908704a8a/James_Blythe_Appointment_Letter_to_Sharon_Kemp.pdf |  |  | 9e7e04afa0f983c1a329b728d25fe631
2026-08-04 | Nottingham City Council: Letter to former Commissioners (24 March 2026) | GOV.UK | Attachment | 2026-03-24 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/69c147fa13101e9908704a86/Minister_Letter_to_Notts_Commissioners.pdf |  |  | 3aed4ba5a6cae16a7bdc7ca1fc2d756f
2026-08-04 | Nottingham City Council: Directions made under the Local Government Act 1999 (24 March 2026) | GOV.UK | Attachment | 2026-03-24 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/69c1756913101e9908704ada/Nottingham_Directions.pdf |  |  | 745a507f92aa4f20356c24d9fddbbcec
2026-08-04 | Nottingham City Council: Explanatory Memorandum (24 March 2026) | GOV.UK | Attachment | 2026-03-24 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/69c174e813101e9908704ad9/Nottingham_Explanatory_Memorandum.pdf |  |  | c384fde51b1381f329d636a0e05ba995
2026-08-04 | Nottingham City Council: Representation (24 March 2026) | GOV.UK | Attachment | 2026-03-24 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/69c14e22bb0dfe55b83e4bab/Nottingham_City_Council_Representation_260211.pdf |  |  | c060c252e02f39bab3c0aedae03b29fa
2026-08-04 | Nottingham City Council: Letter to the Chief Executive (4 February 2026) | GOV.UK | Attachment | 2026-02-04 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/6981aa11f0e5cf1ed2612e50/Letter_to_Nottingham_Chief_Executive.pdf |  |  | 8b487dcc8f1b251da1feaf064d9ae38d
2026-08-04 | Nottingham City Council: Ministerial response to the Commissioners’ fourth report | GOV.UK | Attachment | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/6981a8e23915f71236580144/Minister_Response_to_Commissioners_Report.pdf |  |  | eea4d6fa6a936f82df1a43a3db214be6
2026-08-04 | Nottingham City Council: Commissioners’ fourth report | GOV.UK | Attachment | 2026-02-04 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/6981a50584f2153b11245387/Fourth_Report_Nottingham_City_Council_Commissioners__-_5_Dec_2025.pdf |  |  | e1b0a957888f453ec83abfcd05e8cf74
2026-08-04 | Nottingham City Council: Explanatory Memorandum (updated 21 November 2025) | GOV.UK | Attachment | 2025-11-21 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/691da521d140bbbaa59a2a0a/Updated_Explanatory_Memorandum_-_Nottingham.pdf |  |  | 137eb83be5e8155978a7591feec4fc7b
2026-08-04 | Nottingham City Council: Lead Commissioner appointment letter (Sharon Kemp) | GOV.UK | Attachment | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/691da2e4e39a085bda43ef63/Sharon_Kemp_Nottingham_Appointment_Letter.pdf |  |  | 8e2cce2075f077f6175a910e08201bbc
2026-08-04 | Nottingham City Council: Commissioner appointment letter (Tony McArdle) | GOV.UK | Attachment | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/691da36a513046b952c50044/Tony_McArdle_Nottingham_Appointment_Letter.pdf |  |  | 09e9a5aa3a1f1401eabe7427cc9b47a1
2026-08-04 | Nottingham City Council: Ministerial response to the Commissioners’ third report | GOV.UK | Attachment | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/691da11b0dcbf6343e9a29f9/Minister_McGovern_Response_to_Nottingham_Commissioners.pdf |  |  | 2fba4d086038d9207621361c8eec0240
2026-08-04 | Nottingham City Council: Commissioners’ third report | GOV.UK | Attachment | 2025-11-21 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/691d9f760dcbf6343e9a29ec/Nottingham_Commissioners__third_report.pdf |  |  | f6b056283dee623a67765d5057e64e29
2026-08-04 | Nottingham City Council: Ministerial response to the Commissioners’ second report | GOV.UK | Attachment | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/681b71ad275cb67b18d87031/Nottingham_-_BT_Letter_to_Commissioners.pdf |  |  | 622a9cd39d604a8a09d1df3803e58987
2026-08-04 | Nottingham City Council: Commissioners’ second report | GOV.UK | Attachment | 2025-05-08 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/681b6fba3f1c73824ee3e538/Nottingham_Commissioners_Second_Report_March_2025.pdf |  |  | d0c4aa38cacc84d33879e8a21c14a906
2026-08-04 | Nottingham City Council: Exceptional Financial Support request 2025-26 | GOV.UK | Attachment | 2025-03-13 | Yes | Local, Intervention | Other | https://assets.publishing.service.gov.uk/media/67cae216ade26736dbfa002b/Nottingham_City_Council_-_Exceptional_Financial_Support_request_2025-26.pdf |  |  | 5df9c5bb373b451c02a462f88155b573
2026-08-04 | Nottingham City Council: Ministerial response to Commissioners’ first report | GOV.UK | Attachment | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/675962be79e8a9792b711117/Ministerial_Response_to_Nottingham_Commissioners__first_report.pdf |  |  | 948914f0c28af5425e348ea10c4efb59
2026-08-04 | Nottingham City Council: Commissioners' first report | GOV.UK | Attachment | 2024-12-12 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/675961bf79e8a9792b711115/Nottingham_Commissioners__first_report.pdf |  |  | 3ff8a559cfc576c231c3341457cc3e3b
2026-08-04 | Nottingham City Council Improvement and Assurance Board: final report | GOV.UK | Attachment | 2024-05-16 | Unclear | Local | Internal Controls | /government/publications/nottingham-city-council-improvement-and-assurance-board-final-report/nottingham-city-council-improvement-and-assurance-board-final-report |  |  | df0a933e5e3aa76e7ff8faa75ddab56e
2026-08-04 | ​​Nottingham City Council: Explanatory Memorandum (updated 11 April 2024)​ | GOV.UK | Attachment | 2024-04-11 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/6616bd3156df202ca4ac05fc/NCC_Revised_Explanatory_Memorandum.pdf |  |  | 7ccabb3c8021cc368da2cbd9d2b4340d
2026-08-04 | Nottingham City Council: Lead Commissioner appointment letter (Tony McArdle) | GOV.UK | Attachment | 2024-04-11 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/65d716c3188d77001103887d/Nottingham_City_Council_Lead_Commissioner_appointment_letter__Tony_McArdle_.pdf |  |  | 19ea7843198673d8c167be5949be06c0
2026-08-04 | Nottingham City Council: Commissioner appointment letter (Margaret Lee) | GOV.UK | Attachment | 2024-04-11 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/65d7179b188d77a8d3038774/Nottingham_City_Council_Commissioner_appointment_letter__Margaret_Lee_.pdf |  |  | 85630cbc0e7368b0d87f1000ee3afaa6
2026-08-04 | Nottingham City Council: Commissioner appointment letter (Sharon Kemp) | GOV.UK | Attachment | 2024-04-11 | Yes | Local, Intervention | Governance and Transparency | https://assets.publishing.service.gov.uk/media/6616b31a1a70cf4b92093246/NCC_Commissioner_Appointment_Letter_Sharon_Kemp.pdf |  |  | e7ca97105a4a5b9358a7c7b57168cb53
2026-08-04 | Nottingham City Council: Exceptional Financial Support request 2024-25 | GOV.UK | Attachment | 2024-02-29 | Yes | Local, Intervention | Other | https://assets.publishing.service.gov.uk/media/65df5aeef1cab36b60fc4738/Exceptional_Financial_Support_Letter_-_Nottingham_City_Council_2024-25.pdf |  |  | 30595b99ee22d46036f2e566020f7ad6
2026-08-04 | Nottingham City Council: Letter to the Chief Executive (22 February 2024) | GOV.UK | Attachment | 2024-02-22 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/65d744ec54f1e7001a165885/Nottingham_City_Council_Letter_to_the_Chief_Executive__22_February_2024_.pdf |  |  | 10a0bc76cde45b413d51f54ede47f880
2026-08-04 | Nottingham City Council: Ministerial letter to Sir Tony Redmond (22 February 2024) | GOV.UK | Attachment | 2024-02-22 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/65d71d7f2ab2b3e0f27595ad/Nottingham_City_Council_Ministerial_response_to_Sir_Tony_Redmond__22_February_2024_.pdf |  |  | 1ab8bb28f82ff71064ebd6d3d60f432f
2026-08-04 | Nottingham City Council: Directions made under the Local Government Act 1999 (22 February 2024) | GOV.UK | Attachment | 2024-02-22 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/65d713262197b200117fa80a/Nottingham_City_Council_Directions_made_under_the_Local_Government_Act_1999__22_February_2024_.pdf |  |  | 9ddf0b01939c768e46e11a517a832ed2
2026-08-04 | Nottingham City Council: Explanatory Memorandum (22 February 2024) | GOV.UK | Attachment | 2024-02-22 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/65d713b6188d770011038878/Nottingham_City_Council_Explanatory_Memorandum__22_February_2024_.pdf |  |  | 6c3a9937c1548e83108b1ada5c4e559a
2026-08-04 | Nottingham City Council: Representation (22 February 2024) | GOV.UK | Attachment | 2024-02-22 | Unclear | Local | Other | https://assets.publishing.service.gov.uk/media/65d72394188d77a8d303878c/Nottingham_City_Council_Representation__22_February_2024_.pdf |  |  | 3ff2d1093161f0e8a2973d18e812185a

## Obligations
Obligation ID | Obligation | Source / Trigger | Theme | Owner | Risk Rating | Target Date | Status | Evidence Required | Evidence Location | Sign Off By | Last Updated | Notes | Obligation Level | Linked Actions
OB-A1 | NCC must establish the Continuous Improvement Committee with the required membership including Opposition Leaders, independent external leads for Adults and Children, and Ministerial Envoys. | Nottingham City Council: Directions made under the Local Government Act 1999 (24 March 2026) | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | High | 2026-06-04 | Complete | Committee Terms of Reference published; first meeting held with correct membership. | https://committee.nottinghamcity.gov.uk/documents/g11742/Public%20reports%20pack%2004th-Jun-2026%2014.00%20Improvement%20Committee.pdf | Improvement Committee / John | 2026-08-04 | Completed at the 4 June 2026 Improvement Committee meeting. Was part of the old OB-005 commissioner row. | Periodic
OB-A2 | NCC must prepare and agree the Continuous Service Improvement Plan (CSIP) with the Ministerial Envoys within three months of the 24 March 2026 directions. | 24 March 2026 Directions; Improvement Committee report 4 June 2026 | Governance and Transparency | Sajeeda Rose (Chief Executive) | High | 2026-06-24 | In progress | Improvement Committee endorsement minute; published CSIP document. | https://www.gov.uk/government/collections/statutory-intervention-nottingham-city-council-minded-to-decision | Improvement Committee / Ministerial Envoys | 2026-08-04 | MOST TIME-CRITICAL obligation. Deadline 24 June 2026 = three months from the 24 March 2026 directions. | Statutory | A-009
OB-A3 | NCC must embed improvements in financial management, savings delivery, accounts production, and capital programme governance. | 24 March 2026 Directions; CSIP Financial Sustainability and Management programme | Financial Reporting | Stuart Fair (Corporate Director for Finance and Resources, S151) | High |  | Ongoing | Audit Committee treasury and accounts papers; CSIP performance reporting; six-monthly Improvement Committee reports. | https://committee.nottinghamcity.gov.uk/ieListMeetings.aspx?CommitteeId=1175 | Improvement Committee | 2026-08-04 | SAO Finance: S Fair. Monitored six-monthly via the Improvement Committee. | Monitoring | A-010
OB-A4 | NCC must embed improvements in scrutiny and decision making across the council's governance arrangements. | 24 March 2026 Directions; CSIP Governance, Scrutiny and Decision Making programme | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | Medium |  | Ongoing | Improvement Committee reports; Corporate Scrutiny Committee papers; updated Scheme of Delegation. | https://committee.nottinghamcity.gov.uk/ieListMeetings.aspx?CommitteeId=1175 | Improvement Committee | 2026-08-04 | Ongoing CSIP programme. | Monitoring | A-011
OB-A5 | NCC must embed improvements in risk management and internal audit, including aligning the internal audit function with Local Audit Office standards and guidance and ensuring synergy with external assurance. | 24 March 2026 Directions; CSIP Risk Management and Internal Audit programme | Internal Controls | Lynne Dowdican (Head of Internal Audit) | High |  | Ongoing | Internal Audit Annual Plan and progress reports to Audit Committee; Head of Internal Audit opinion; alignment note against LAO standards. | https://committee.nottinghamcity.gov.uk/ieListMeetings.aspx?CommitteeId=145 | Audit Committee | 2026-08-04 | Direct CSIP obligation: internal audit must align with LAO standards. Supported by D Bowring (Risk). | Monitoring | A-012
OB-A6 | NCC must cooperate with the Ministerial Envoys, provide access, and respond to their recommendations. | 24 March 2026 Directions | Governance and Transparency | Sajeeda Rose (Chief Executive) | High |  | Ongoing | Improvement Committee meeting records showing Envoy attendance; responses to Envoy recommendations. | https://www.gov.uk/government/collections/statutory-intervention-nottingham-city-council-minded-to-decision | Chief Executive / Improvement Committee | 2026-08-04 | Since 24 March 2026 the oversight structure uses Ministerial Envoys, not Commissioners. | Monitoring | A-013
OB-A7 | NCC must respond to each recommendation in the external auditor's Annual Report and Audit Findings (ISA 260). | Audit Committee 27 March 2026; External Audit Findings 2024/25 | Financial Reporting | Gareth Robinson (Director of Finance) | High | 2026-07-31 | In progress | Management response document; Audit Committee minute noting acceptance; completed action evidence for each recommendation. | https://committee.nottinghamcity.gov.uk/ieListMeetings.aspx?CommitteeId=145 | Audit Committee | 2026-08-04 | Tie target to the next Audit Committee cycle. | Periodic | A-014, A-034
OB-A8 | NCC must produce and publish audited accounts with a signed audit opinion. | Accounts and Audit Regulations 2015; Audit Committee work programme | Financial Reporting | Stuart Fair (Corporate Director for Finance and Resources, S151) | High | 2026-09-30 | In progress | Published Statement of Accounts; auditor's opinion; note on any disclaimer. |  | Audit Committee | 2026-08-04 | Evidence Location must link to the SPECIFIC year's document on the Statement of Accounts page, not the homepage: https://www.nottinghamcity.gov.uk/your-council/about-the-council/statement-of-accounts-and-reports/ | Enduring | A-015, A-035
OB-A9 | NCC must produce and publish an Annual Governance Statement reflecting the council's current governance position and any significant weaknesses. | Accounts and Audit Regulations 2015; Audit Committee work programme July 2026 | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | High | 2026-07-31 | In progress | Published AGS; Audit Committee approval minute. | https://nottinghamcity.gov.uk | Audit Committee | 2026-08-04 | Target: July 2026 committee cycle. Draft AGS 2024/25 confirmed published online; awaiting Audit Committee approval minute. | Enduring | A-016
OB-A10 | NCC must understand and plan for how the Local Audit Office (LAO) transition affects its audit arrangements, and brief the Audit Committee. | PSAA abolition and Local Audit Office transition | Audit Procurement | Lynne Dowdican (Head of Internal Audit) | High | 2026-09-30 | In progress | Audit Committee briefing note on LAO implications; updated audit plan if needed. | https://assets.publishing.service.gov.uk/media/6926f871345e31ab14ecf524/Local_Audit_Transition_Plan.pdf (MHCLG Local Audit Transition Plan, Nov 2025 — Annex A carries the milestone timeline); https://www.gov.uk/government/organisations/local-audit-office | Audit Committee | 2026-08-04 | CORRECTED 4 Aug 2026 against the MHCLG Local Audit Transition Plan (Nov 2025), which states PSAA's contracts with audit firms 'have recently been extended until 2030' — the tracker previously said 2027/28, understating the horizon by two years. Auditor appointment and contracting duties transfer to the LAO in Spring 2027, with PSAA staff and the existing contracts novating across. Bill Butler is CONFIRMED as LAO Chair from 1 July 2026 (previously recorded as preferred candidate). Was the old OB-002. | Monitoring | A-005
OB-A11 | NCC must progress the open items on the Audit Committee Recommendation Tracker through to completion (see linked actions OB-A11.1, .2, .3). | Audit Committee minutes 20 February 2026; Recommendation Tracker | Governance and Transparency | Kate Morris (Scrutiny and Audit Support Officer) | Medium | 2026-07-31 | In progress | Recommendation Tracker rows moved from Pending to Responded; completion evidence for each sub-action. | https://committee.nottinghamcity.gov.uk/ieListMeetings.aspx?CommitteeId=145 | Audit Committee | 2026-08-04 | Parent obligation. Three sub-actions live in the Actions tab: A11.1 (exemption benchmarking), A11.2 (Table 5 clarification), A11.3 (UN PRI/UNGP legal briefing). | Periodic | A-001, A-002, A-003
OB-A12 | NCC must integrate transitional accounting baselines derived from new oversight standards into local audit workflows. | Bill Butler named as preferred candidate for Local Audit Office Chair PSAA (8 June 2026) | Audit Procurement | Lynne Dowdican (Head of Internal Audit) | High | 2026-09-30 | In progress | Alignment strategy document approved by Audit Committee referencing new LAO framework parameters. | https://www.gov.uk/government/publications/local-audit-office-chair-appointment | Audit Committee | 2026-08-04 | NEW IMMINENT REQUIREMENT tracking transition handovers before ultimate PSAA abolition. | Periodic | A-006
OB-A13 | NCC must have an audit committee and arrange for it to exercise the four statutory functions in section 33A of the Local Audit and Accountability Act 2014: reviewing and scrutinising financial affairs; reviewing and assessing risk management, internal control and governance arrangements; reviewing and assessing economy, efficiency and effectiveness of resource use; and making reports and recommendations to the authority. | Section 94, English Devolution and Community Empowerment Act 2026 (inserting s.33A into the Local Audit and Accountability Act 2014), commenced for Category 1 authorities from 15 July 2026 by SI 2026/812; MHCLG letter to Section 151 Officers, 31 July 2026 | Governance and Transparency | Stuart Fair (Corporate Director for Finance and Resources, S151) | High | 2026-09-25 | In progress | Audit Committee terms of reference mapped against the four s.33A functions; constitution showing the committee is established; record of independent member appointment once the membership regulations are in force. | https://www.legislation.gov.uk/ukpga/2014/2/section/33A (the duty); https://www.legislation.gov.uk/uksi/2026/812/made (SI 2026/812, commenced it 15 July 2026); evidence/2026-07-31-MHCLG-audit-committee-requirement.pdf (MHCLG letter to S151 Officers — not published on GOV.UK, filed alongside this tracker) | Audit Committee | 2026-08-04 | STATUTORY DUTY IN FORCE since 15 July 2026. MHCLG expects most authorities already comply and asks to be told of any difficulty (localaudit@communities.gov.uk). The independent member requirement is NOT yet in force — s.94 provides for further regulations on membership, appointments and allowances, to be followed by statutory guidance. MHCLG encourages authorities without an independent member to begin recruitment now so they are ready when the regulations commence. | Enduring | A-027, A-028, A-029
OB-A14 | NCC must onboard the newly appointed Political Envoy and provide the briefings and access needed for the envoy to discharge the advisory role under the de-escalated intervention arrangements. | MHCLG appointment letter to Sir Stephen Houghton CBE, 15 July 2026 (James Blythe, Deputy Director, Local Government Stewardship and Interventions), appointing him Political Envoy for the purposes of the Directions made 24 March 2026 under section 15(5) of the Local Government Act 1999 | Governance and Transparency | Sajeeda Rose (Chief Executive) | High | 2026-09-24 | Not started | Schedule of induction and advisory sessions; reporting matrix defining the advisory boundary; budget provision for envoy fees; records submitted to the Continuous Improvement Committee. | https://www.gov.uk/government/publications/nottingham-city-council-ministerial-envoy-appointment-letter-15-july-2026 | Chief Executive / Continuous Improvement Committee | 2026-08-04 | Sir Stephen Houghton CBE joins Sharon Kemp, who is Lead Envoy; the Envoys may act jointly or severally and are accountable to the Secretary of State. The letter asks them to provide support 'in an advisory and mentoring capacity', particularly on the Best Value themes of Continuous Improvement and Service Delivery. TWO POINTS THE APPOINTMENT LETTER PUTS ON NCC: (1) fees of GBP 800 per day up to 75 days a year, plus reasonable expenses, are the Authority's responsibility to meet — a liability of up to GBP 60,000 a year per envoy that needs budget provision; (2) the Secretary of State has asked the Envoys to report within the first six months of the intervention, which runs from the 24 March 2026 Directions, hence the target date. Complements OB-A1, which covers Envoy membership of the Continuous Improvement Committee. | Periodic | A-030, A-031, A-032
OB-L1 | NCC must continue to work with other Nottinghamshire councils to define, coordinate, and implement safe day-one establishment of a new unitary authority. | 24 March 2026 Directions; CSIP LGR priority service improvement area | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High |  | Ongoing | Joint LGR committee papers; transition programme updates to Improvement Committee; cooperation records with other councils. | https://www.gov.uk/government/collections/nottinghamshire-and-nottingham-local-government-reorganisation | Chief Executive / Improvement Committee | 2026-08-04 | See also OB-L8 on the MHCLG Devolution Framework Explainers. LGR sits under the Chief Executive and the Director of Policy. MHCLG issued non-statutory staffing issues guidance on 16 July 2026 covering appointment and transfer of employees to the new single-tier councils; gap analysis and staff consultation tracked as A-025 and A-026. | Monitoring | A-017, A-021, A-022, A-023, A-025, A-026
OB-L2 | NCC must track the MHCLG consultation decision and respond to the statutory order implications for Nottinghamshire and Nottingham. | Secretary of State decision letter to Nottinghamshire and Nottingham council leaders, 16 July 2026; HCWS286 written ministerial statement | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High |  | Ongoing | Council response to consultation; record of statutory order decision; legal advice on transition implications. | https://assets.publishing.service.gov.uk/media/6a58d3105ca06bf11ccb42f9/Local_government_reorganisation_-_decision_letter_to_Nottinghamshire_and_Nottingham_council_leaders.pdf | Chief Executive | 2026-08-04 | CONSULTATION DECISION MADE 16 July 2026: Secretary of State confirmed the two-unitary 'modified' option — 'Southwest' (Nottingham City plus wards from Broxtowe, Gedling, Rushcliffe) and 'North and East' (Ashfield, Bassetlaw, Mansfield, Newark and Sherwood plus remaining wards). Shadow elections confirmed May 2027 (replacing scheduled local elections); implementation targeted April 2028. Ministerial Envoy named as Sharon Kemp. This is NOT yet OB-L6's trigger: the Structural Changes Order (the statutory instrument itself) is still subject to Parliamentary approval — officials to write separately with the implementation timeline. OB-L6 becomes live only when that Order is made. | Monitoring | A-018
OB-L3 | NCC must work toward safe and legal day-one establishment of the new unitary authority, including governance, service continuity, and asset and liability planning. | CSIP LGR priority area; MHCLG LGR implementation guidance (May 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | High | 2027-05-01 | Ongoing | Transition programme plan; governance framework for shadow authority; service continuity planning documents. | https://www.gov.uk/government/collections/nottinghamshire-and-nottingham-local-government-reorganisation | Chief Executive / Improvement Committee | 2026-08-04 | Planning horizon: shadow authority elections CONFIRMED May 2027 (SoS decision letter 16 July 2026, replacing scheduled local elections); Vesting Day targeted 1 April 2028. | Monitoring | A-004
OB-L4 | The internal audit plan must cover LGR transition risks including service demerger, asset and liability transfer, and governance during the shadow authority phase. | CSIP Risk Management and Internal Audit programme; seeded OB-004 | LGR Transition | Lynne Dowdican (Head of Internal Audit) | High | 2026-10-31 | In progress | Updated Internal Audit Annual Plan with an LGR transition section; Audit Committee approval. |  | Audit Committee | 2026-08-04 | Cross-track: also an Internal Controls obligation. Was the old OB-004. | Periodic | A-019
OB-L5 | NCC must review its governance, audit committee arrangements, and successor body governance in light of the English Devolution and Community Empowerment Act 2026 transparency and accountability codes. | English Devolution and Community Empowerment Act 2026 (Royal Assent confirmed) | Governance and Transparency | Beth Brown (Strategic Director of Legal and Governance) | Medium | 2026-07-31 | In progress | Formal gap analysis report to the July 2026 Audit Committee verifying the successor-body governance framework matches the 2026 Act, referencing the relevant Act sections against the current Audit Committee Terms of Reference and the proposed successor body governance model. |  | Audit Committee | 2026-08-04 | LGR legislative track. Detailed implementation timeline firms up as statutory guidance is issued. Was the old OB-001. | Periodic | A-008
OB-L6 | On issue of the final Statutory Boundary Order, the Section 151 Officer must review asset and liability arrangements for any items planned for transfer to the new unitary authority. | Statutory Boundary Order for the Nottingham/Nottinghamshire unitary structure (pending) | LGR Transition | Stuart Fair (Corporate Director for Finance and Resources, S151) | High |  | Not started | S151 finance review of asset and liability transfer arrangements; report to Audit / Improvement Committee. |  | Section 151 Officer / Audit Committee | 2026-08-04 | TRIGGER PENDING: this obligation only becomes live when the final Statutory Boundary Order is published (Guide Part 6). It is a formal finance review obligation, not a freeze of the asset registry — that remains the S151 Officer's decision. Set the Target Date when the order lands. | Periodic | A-020
OB-L7 | NCC must optimize regional demerger models to comply with newly issued national administrative transformation frameworks. | Local government reorganisation: implementation guidance GOV.UK (8 June 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | Medium |  | Ongoing | LGR working team minutes detailing structural compliance parameters mapped against the June 2026 layout guides. | https://www.gov.uk/government/publications/local-government-reorganisation-implementation-guidance | Chief Executive / Improvement Committee | 2026-08-04 | NEW GUIDANCE INCORPORATION: ensures technical migration alignment with central criteria. | Monitoring | A-007
OB-L8 | NCC must track the MHCLG Devolution Framework Explainers and assess how the statutory functions they set out for Strategic Authorities shape the operating model of the new unitary authorities. | English Devolution and Community Empowerment Act 2026: Devolution Framework Explainers, MHCLG (last updated 8 June 2026) | LGR Transition | James Rhodes (Director of Policy, Performance and Communications) | Medium | 2026-10-31 | Not started | Gap analysis mapping NCC service lines against the Strategic Authority functions in the Explainers, reported to the LGR programme board. | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-devolution-framework-explainers | Chief Executive / Improvement Committee | 2026-08-04 | SCOPE NOTE: the Explainers set out the statutory functions of STRATEGIC AUTHORITIES. NCC is not a Strategic Authority — EMCCA is — so these are not a duty on NCC directly. They matter because the new unitaries will be constituent councils of EMCCA, so the Explainers define the boundary between what EMCCA holds and what the unitaries hold. Monitoring, not compliance. | Monitoring | A-033

## Actions
Action ID | Parent Obligation ID | Action | Owner | Start Date | Due Date | Status | Percent Complete | Evidence Link | Notes
A-001 | OB-A11 | Publish a benchmarking exercise comparing NCC's contract exemption rates against neighbouring Nottinghamshire authorities. | A Spice / D Cafferty (Procurement) |  | 2026-07-31 | Not started | 0 |  | OB-A11.1 — Contract Procedure Rules Exemption Benchmarking. Evidence: formal benchmarking appendix in the Procurement Annual Report. Target: July 2026 Audit Committee.
A-002 | OB-A11 | Provide a clarification note splitting debt and investments between the General Fund and the Housing Revenue Account (HRA) in Table 5 of the Treasury Management Report. | Gareth Robinson (Director of Finance) | 2026-04-15 | 2026-06-30 | Complete | 100 | nottinghamcity.gov.uk | OB-A11.2 — Treasury Management Table 5 Clarification. Evidence: signed addendum note or updated table in the finalised Treasury Management Strategy. Target: June 2026 Audit Committee.
A-003 | OB-A11 | Provide a formal briefing note once legal advice on UN PRI (Principles for Responsible Investment) and UNGP (UN Guiding Principles) compliance frameworks is received. | Beth Brown (Strategic Director of Legal and Governance) |  | 2026-06-30 | Not started | 0 |  | OB-A11.3 — UN PRI and UNGP Legal Briefing. Evidence: distributed legal briefing note; logged in committee minutes or correspondence record. Target: June 2026 Audit Committee.
A-004 | OB-L3 | Scope and procure the day-one IT systems and data migration required for the new unitary authority. | James Rhodes (Director of Policy, Performance and Communications) | 2026-06-01 | 2027-02-28 | Not started | 0 |  | Demonstrates the Part 9 cross-track financial gateway: this LGR action involves procurement / IT system migration, so the S151 sign-off note is attached automatically. ⚠️ Procurement/capital action: requires Section 151 sign-off under current spending controls before proceeding. Confirm with Stuart Fair or Gareth Robinson.
A-005 | OB-A10 | Prepare an Audit Committee briefing note on the LAO transition and its implications for NCC's PSAA-procured audit contract, which now runs to 2030. | Lynne Dowdican (Head of Internal Audit) |  | 2026-09-30 | Not started | 0 | https://assets.publishing.service.gov.uk/media/6926f871345e31ab14ecf524/Local_Audit_Transition_Plan.pdf | Supports OB-A10. Milestones from the MHCLG Local Audit Transition Plan (Nov 2025), Annex A: LAO legally established Autumn 2026; auditor appointment and contracting duties, PSAA staff and the existing contracts transfer to the LAO Spring 2027. Bill Butler CONFIRMED as LAO Chair from 1 July 2026 (was recorded as preferred candidate).
A-006 | OB-A12 | Review structural transitional reporting regulations issued by the preferred LAO Chair candidate and adjust internal audit backstop clearance milestones accordingly. | Lynne Dowdican (Head of Internal Audit) | 2026-06-09 | 2026-09-30 | Not started | 0 |  | NEW ACTION: Leverages 8 June 2026 intelligence on Bill Butler's framework metrics.
A-007 | OB-L7 | Perform an internal option appraisal to cross-examine whether the newly introduced June 2026 GOV.UK reorganisation layout guidance changes boundary line migration costings. | James Rhodes (Director of Policy, Performance and Communications) | 2026-06-09 | 2026-08-31 | Not started | 0 |  | NEW ACTION: Triggered by 8 June 2026 GOV.UK Implementation Guidance paper updates.
A-008 | OB-L5 | Draft the formal accountability framework and code alignment overview mandated by the recent Royal Assent confirmation of the English Devolution Act. | Beth Brown (Strategic Director of Legal and Governance) | 2026-06-09 | 2026-07-31 | Not started | 0 |  | NEW ACTION: Directly links legislative confirmation of Act 2026 to the July 2026 Audit Committee agenda.
A-009 | OB-A2 | Coordinate final verification review and ensure physical sign-off endorsement of the complete CSIP text block by Ministerial Envoys. | Sajeeda Rose (Chief Executive) | 2026-06-05 | 2026-06-24 | In progress | 50 |  | NEW ACTION: Drives the immediate execution threshold for the statutory 3-month target deadline.
A-010 | OB-A3 | Review financial management, savings delivery, accounts production, and capital programme improvements at the six-monthly Improvement Committee report and record the check. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-07-11 | 2026-12-31 | In progress | 0 |  | Standing Monitor action — six-monthly cycle; roll the due date forward after each review.
A-011 | OB-A4 | Review scrutiny and decision-making improvements at each Improvement Committee report and record the check, filing Corporate Scrutiny papers and Scheme of Delegation updates as evidence. | Beth Brown (Strategic Director of Legal and Governance) | 2026-07-11 | 2026-12-31 | In progress | 0 |  | Standing Monitor action — roll the due date forward after each review.
A-012 | OB-A5 | Prepare the internal audit alignment note against Local Audit Office standards and guidance, and present progress reports at each Audit Committee. | Lynne Dowdican (Head of Internal Audit) | 2026-07-11 | 2026-07-31 | In progress | 0 |  | First deliverable under the standing CSIP internal-audit obligation; target the July 2026 Audit Committee.
A-013 | OB-A6 | Record Ministerial Envoy attendance and the council's responses to Envoy recommendations at each Improvement Committee meeting. | Sajeeda Rose (Chief Executive) | 2026-07-11 | 2026-09-30 | In progress | 0 |  | Standing Engage action — evidence accrues each committee cycle.
A-014 | OB-A7 | Produce the management response document to each recommendation in the external auditor's Annual Report (ISA 260) and secure the Audit Committee acceptance minute. | Gareth Robinson (Director of Finance) | 2026-07-11 | 2026-07-31 | In progress | 0 |  | Delivers OB-A7 at the July 2026 Audit Committee cycle.
A-015 | OB-A8 | Produce and publish the 2024/25 Statement of Accounts with the auditor's opinion (noting any disclaimer), and link the specific year's document on the accounts page as evidence. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-07-11 | 2026-09-30 | In progress | 0 |  | Recurring Produce action under the enduring Accounts and Audit Regulations duty — repeats each reporting year.
A-016 | OB-A9 | Secure Audit Committee approval of the published draft Annual Governance Statement 2024/25 and link the approval minute as evidence. | Beth Brown (Strategic Director of Legal and Governance) | 2026-07-11 | 2026-07-31 | In progress | 50 |  | Draft AGS confirmed published online; remaining step is the approval minute at the July 2026 Audit Committee.
A-017 | OB-L1 | File joint LGR committee papers, transition programme updates to the Improvement Committee, and cooperation records with the other Nottinghamshire councils each committee cycle. | James Rhodes (Director of Policy, Performance and Communications) | 2026-07-11 | 2026-09-30 | In progress | 0 |  | Standing Engage action for the joint LGR programme.
A-018 | OB-L2 | Monitor MHCLG announcements for the LGR consultation decision and the Statutory Boundary Order; on publication, set OB-L6's target date and notify the Section 151 Officer immediately. | James Rhodes (Director of Policy, Performance and Communications) | 2026-07-11 | 2026-08-31 | In progress | 40 | https://assets.publishing.service.gov.uk/media/6a58d3105ca06bf11ccb42f9/Local_government_reorganisation_-_decision_letter_to_Nottinghamshire_and_Nottingham_council_leaders.pdf | Consultation decision half done: SoS confirmed the two-unitary option on 16 July 2026 (Southwest / North and East, elections May 2027). Still monitoring for the Structural Changes Order itself, which officials said would follow separately and remains subject to Parliamentary approval — that is what triggers OB-L6 (Guide Part 12).
A-019 | OB-L4 | Update the Internal Audit Annual Plan with an LGR transition risk section (service demerger, asset and liability transfer, shadow authority governance) and secure Audit Committee approval. | Lynne Dowdican (Head of Internal Audit) | 2026-07-11 | 2026-10-31 | Not started | 0 |  | Delivers OB-L4; cross-track with Internal Controls.
A-020 | OB-L6 | On issue of the final Statutory Boundary Order, complete the Section 151 review of asset and liability transfer arrangements and report to the Audit / Improvement Committee. | Stuart Fair (Corporate Director for Finance and Resources, S151) |  |  | Not started | 0 |  | TRIGGER PENDING: dates are set when the Statutory Boundary Order is published (see A-018).
A-021 | OB-L1 | Participate in joint implementation governance. | James Rhodes (Director of Policy, Performance and Communications) | 2026-07-16 |  | Not started | 0 |  | Joint programme governance structure to be agreed and implemented.
A-022 | OB-L1 | Work with Nottinghamshire authorities on transition arrangements. | James Rhodes (Director of Policy, Performance and Communications) | 2026-07-16 |  | Not started | 0 |  | Joint programme to be set out and ownership and accountabilities to be defined and progress monitored.
A-023 | OB-L1 | Support development of new operating models, staffing arrangements and service integration plans. | Lee Mann (Strategic Director of HR & EDI) | 2026-07-16 |  | Not started | 0 |  | Gather existing establishment and operating model details. Support planning for new establishment and operating models. Ensure timely onboarding processes.
A-025 | OB-L1 | Review the MHCLG local government reorganisation staffing issues guidance (16 July 2026) and complete a gap analysis against current demerger and staffing transition assumptions. | Lee Mann (Strategic Director of HR & EDI) | 2026-08-04 | 2026-09-30 | Not started | 0 | https://www.gov.uk/government/publications/local-government-reorganisation-staffing-issues-guidance | Checks the emerging operating model against central expectations on appointment and transfer of staff to the new single-tier councils. Feeds A-023.
A-026 | OB-L1 | Use the MHCLG staffing guidance overview in joint-council consultation with trade unions and staff on day-one staffing arrangements. | Lee Mann (Strategic Director of HR & EDI) | 2026-08-04 | 2026-10-31 | Not started | 0 | https://www.gov.uk/government/publications/local-government-reorganisation-staffing-issues-guidance | The 3-page overview published alongside the full guidance is the version intended for staff and union consultation.
A-027 | OB-A13 | Map the Audit Committee's terms of reference against the four statutory functions in s.33A of the Local Audit and Accountability Act 2014 and report the result to the Audit Committee, identifying any constitutional amendment needed. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-08-04 | 2026-09-25 | Not started | 0 | https://www.legislation.gov.uk/ukpga/2026/23/section/94/enacted | Duty in force since 15 July 2026. MHCLG expects most authorities already comply, so this confirms compliance rather than builds it — and gives a documented basis for telling MHCLG if any difficulty is foreseen. Target: 25 September 2026 Audit Committee.
A-028 | OB-A13 | Launch recruitment for an independent member of the Audit Committee, including a public advertisement and role profile, ahead of the membership regulations coming into force. | Beth Brown (Strategic Director of Legal and Governance) | 2026-08-04 | 2026-10-15 | Not started | 0 |  | Evidence: live public advertisement on the NCC jobs portal, role profile, and the appointment route through to committee. MHCLG encourages early recruitment — the independent member requirement is not yet in force and will be commenced by regulations made under s.94, so this is preparation rather than a duty in force. Starting now avoids a compliance gap on commencement.
A-029 | OB-A13 | Monitor for the s.94 regulations on audit committee membership, appointments and allowances, and the statutory guidance that follows them; on publication, reassess the terms of reference and the independent member appointment against the final requirements. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-08-04 |  | Not started | 0 |  | TRIGGER PENDING: dates are set when the membership regulations are laid. Government has said this will happen 'when parliamentary time allows', so there is no announced date to work to (Guide Part 12).
A-030 | OB-A14 | Coordinate the initial political and executive induction sessions with Political Envoy Sir Stephen Houghton CBE. | Sajeeda Rose (Chief Executive) | 2026-08-04 | 2026-09-15 | Not started | 0 |  | Evidence: schedule of initial advisory sessions submitted to the Continuous Improvement Committee.
A-031 | OB-A14 | Update the executive reporting matrix to define the advisory and mentoring boundaries of the Envoy role, covering both the Lead Envoy and the Political Envoy and their power to act jointly or severally. | Sajeeda Rose (Chief Executive) | 2026-08-04 | 2026-09-30 | Not started | 0 | https://www.gov.uk/government/publications/nottingham-city-council-letter-to-council-leader-15-july-2026 | Evidence: framework document signed off by the Leader (Cllr Neghat Khan) and Executive Panel. Records the distinction between the former Commissioner powers and the current advisory and mentoring role.
A-032 | OB-A14 | Confirm budget provision for Political Envoy fees and expenses, and put in place the approval route for exceeding the 75-day annual cap. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-08-04 | 2026-09-30 | Not started | 0 |  | The appointment letter makes envoy costs the Authority's responsibility: GBP 800 per day, maximum 75 days a year, plus reasonable expenses at senior officer rates. The cap cannot be exceeded without prior Secretary of State approval, so the route needs to exist before it is needed.
A-033 | OB-L8 | Map NCC's single-tier operational workflows against the Strategic Authority functions set out in the MHCLG Devolution Framework Explainers, identifying which service lines sit with EMCCA and which with the new unitary authorities. | James Rhodes (Director of Policy, Performance and Communications) | 2026-08-04 | 2026-10-31 | Not started | 0 | https://www.gov.uk/government/publications/english-devolution-and-community-empowerment-bill-devolution-framework-explainers | Evidence: structural gap analysis signed off by the Director of Policy and reported to the LGR programme board. Establishes the EMCCA / unitary boundary before day-one service allocation is fixed.
A-034 | OB-A7 | Confirm whether NCC gave MHCLG permission for its auditor to share the Auditor's Annual Report, the ISA 260 and the audit capacity assessment with the Department, and resolve the position with MHCLG if it did not. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-08-04 | 2026-09-25 | Not started | 0 | https://assets.publishing.service.gov.uk/media/692992e6a245b0985f034280/Ministerial_letter_to_local_bodies.pdf | RETROSPECTIVE CHECK — BOTH DEADLINES HAVE PASSED. The Minister of State wrote to Chief Executives, CFOs and Leaders on 27 November 2025 asking for the AAR and ISA 260 by 31 March 2026 and an auditor capacity assessment by end July 2026. The letter says that where permission is not given, MHCLG officials will follow up directly. There is no record either way in the tracker, so the answer needs establishing rather than assuming. Evidence: the permission response to the audit firm, or correspondence with MHCLG.
A-035 | OB-A8 | Agree the build-back trajectory with the external auditor for clearing any backstop-related disclaimed opinions, working to the 30 November 2028 backstop, and report the trajectory to the Audit Committee. | Stuart Fair (Corporate Director for Finance and Resources, S151) | 2026-08-04 | 2026-11-27 | Not started | 0 | https://assets.publishing.service.gov.uk/media/692992e6a245b0985f034280/Ministerial_letter_to_local_bodies.pdf | The build-back programme aims to clear backstop-related disclaimers by the end of 2027/28, for which the backstop date is 30 November 2028. Government has said progress is slower than hoped and that NO FURTHER build-back grant was paid in 2025/26, with the funding model reviewed in summer and autumn 2026 — so the cost of this sits with NCC unless that review changes it. The letter also stresses that authorities must adequately resource their finance functions to supply audit evidence.

## Evidence Gaps
Type | ID | Owner | Evidence needed | Sign off / Parent | Target | Where it should land | Obtained?
Obligation | OB-A8 | Stuart Fair (Corporate Director for Finance and Resources, S151) | Published Statement of Accounts; auditor's opinion; note on any disclaimer. | Audit Committee | 2026-09-30 | Audit Committee papers
Obligation | OB-L4 | Lynne Dowdican (Head of Internal Audit) | Updated Internal Audit Annual Plan with an LGR transition section; Audit Committee approval. | Audit Committee | 2026-10-31 | Audit Committee papers
Obligation | OB-L5 | Beth Brown (Strategic Director of Legal and Governance) | Formal gap analysis report to the July 2026 Audit Committee verifying the successor-body governance framework matches the 2026 Act, referencing the relevant Act sections against the current Audit Committee Terms of Reference and the proposed successor body governance model. | Audit Committee | 2026-07-31 | Audit Committee papers
Obligation | OB-L6 | Stuart Fair (Corporate Director for Finance and Resources, S151) | S151 finance review of asset and liability transfer arrangements; report to Audit / Improvement Committee. | Section 151 Officer / Audit Committee |  | Audit Committee papers
Action | A-001 | A Spice / D Cafferty (Procurement) | Publish a benchmarking exercise comparing NCC's contract exemption rates against neighbouring Nottinghamshire authorities. | OB-A11 | 2026-07-31 | Internal - council document store
Action | A-003 | Beth Brown (Strategic Director of Legal and Governance) | Provide a formal briefing note once legal advice on UN PRI (Principles for Responsible Investment) and UNGP (UN Guiding Principles) compliance framewo | OB-A11 | 2026-06-30 | Internal - council document store
Action | A-004 | James Rhodes (Director of Policy, Performance and Communications) | Scope and procure the day-one IT systems and data migration required for the new unitary authority. | OB-L3 | 2027-02-28 | Internal - council document store
Action | A-006 | Lynne Dowdican (Head of Internal Audit) | Review structural transitional reporting regulations issued by the preferred LAO Chair candidate and adjust internal audit backstop clearance mileston | OB-A12 | 2026-09-30 | Internal - council document store
Action | A-007 | James Rhodes (Director of Policy, Performance and Communications) | Perform an internal option appraisal to cross-examine whether the newly introduced June 2026 GOV.UK reorganisation layout guidance changes boundary li | OB-L7 | 2026-08-31 | Internal - council document store
Action | A-008 | Beth Brown (Strategic Director of Legal and Governance) | Draft the formal accountability framework and code alignment overview mandated by the recent Royal Assent confirmation of the English Devolution Act. | OB-L5 | 2026-07-31 | Internal - council document store
Action | A-009 | Sajeeda Rose (Chief Executive) | Coordinate final verification review and ensure physical sign-off endorsement of the complete CSIP text block by Ministerial Envoys. | OB-A2 | 2026-06-24 | Internal - council document store
Action | A-010 | Stuart Fair (Corporate Director for Finance and Resources, S151) | Review financial management, savings delivery, accounts production, and capital programme improvements at the six-monthly Improvement Committee report | OB-A3 | 2026-12-31 | Internal - council document store
Action | A-011 | Beth Brown (Strategic Director of Legal and Governance) | Review scrutiny and decision-making improvements at each Improvement Committee report and record the check, filing Corporate Scrutiny papers and Schem | OB-A4 | 2026-12-31 | Internal - council document store
Action | A-012 | Lynne Dowdican (Head of Internal Audit) | Prepare the internal audit alignment note against Local Audit Office standards and guidance, and present progress reports at each Audit Committee. | OB-A5 | 2026-07-31 | Internal - council document store
Action | A-013 | Sajeeda Rose (Chief Executive) | Record Ministerial Envoy attendance and the council's responses to Envoy recommendations at each Improvement Committee meeting. | OB-A6 | 2026-09-30 | Internal - council document store
Action | A-014 | Gareth Robinson (Director of Finance) | Produce the management response document to each recommendation in the external auditor's Annual Report (ISA 260) and secure the Audit Committee accep | OB-A7 | 2026-07-31 | Internal - council document store
Action | A-015 | Stuart Fair (Corporate Director for Finance and Resources, S151) | Produce and publish the 2024/25 Statement of Accounts with the auditor's opinion (noting any disclaimer), and link the specific year's document on the | OB-A8 | 2026-09-30 | Internal - council document store
Action | A-016 | Beth Brown (Strategic Director of Legal and Governance) | Secure Audit Committee approval of the published draft Annual Governance Statement 2024/25 and link the approval minute as evidence. | OB-A9 | 2026-07-31 | Internal - council document store
Action | A-017 | James Rhodes (Director of Policy, Performance and Communications) | File joint LGR committee papers, transition programme updates to the Improvement Committee, and cooperation records with the other Nottinghamshire cou | OB-L1 | 2026-09-30 | Internal - council document store
Action | A-019 | Lynne Dowdican (Head of Internal Audit) | Update the Internal Audit Annual Plan with an LGR transition risk section (service demerger, asset and liability transfer, shadow authority governance | OB-L4 | 2026-10-31 | Internal - council document store
Action | A-020 | Stuart Fair (Corporate Director for Finance and Resources, S151) | On issue of the final Statutory Boundary Order, complete the Section 151 review of asset and liability transfer arrangements and report to the Audit / | OB-L6 |  | Internal - council document store
Action | A-021 | James Rhodes (Director of Policy, Performance and Communications) | Participate in joint implementation governance. | OB-L1 |  | Internal - council document store
Action | A-022 | James Rhodes (Director of Policy, Performance and Communications) | Work with Nottinghamshire authorities on transition arrangements. | OB-L1 |  | Internal - council document store
Action | A-023 | Lee Mann (Strategic Director of HR & EDI) | Support development of new operating models, staffing arrangements and service integration plans. | OB-L1 |  | Internal - council document store
Action | A-028 | Beth Brown (Strategic Director of Legal and Governance) | Launch recruitment for an independent member of the Audit Committee, including a public advertisement and role profile, ahead of the membership regula | OB-A13 | 2026-10-15 | Internal - council document store
Action | A-029 | Stuart Fair (Corporate Director for Finance and Resources, S151) | Monitor for the s.94 regulations on audit committee membership, appointments and allowances, and the statutory guidance that follows them; on publicat | OB-A13 |  | Internal - council document store
Action | A-030 | Sajeeda Rose (Chief Executive) | Coordinate the initial political and executive induction sessions with Political Envoy Sir Stephen Houghton CBE. | OB-A14 | 2026-09-15 | Internal - council document store
Action | A-032 | Stuart Fair (Corporate Director for Finance and Resources, S151) | Confirm budget provision for Political Envoy fees and expenses, and put in place the approval route for exceeding the 75-day annual cap. | OB-A14 | 2026-09-30 | Internal - council document store